# Issue & Escalation Procedures

Mastech Digital — Informatica Platform Assets

Structured issue management and escalation framework for Informatica IDMC program delivery.

| Document | Issue & Escalation Procedures |
| --- | --- |
| Category | Governance Library |
| Document ID | #55 |
| Version | 1.0 |
| Date | February 2026 |
| Author | Mastech Digital — Informatica Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Informatica IDMC (IICS) – Early 2026 |
| Next Review | August 2026 |

# Executive Summary

Timely identification, classification, and resolution of issues is essential to maintaining program momentum and stakeholder confidence. This document defines the issue management lifecycle, severity classification matrix, escalation paths, and response time SLAs for Informatica IDMC programs. It includes communication templates, root cause analysis procedures, and war room protocols for critical incidents.

# Table of Contents

1.0  Issue Management Lifecycle

2.0  Severity Classification

3.0  Escalation Matrix

4.0  Response Time SLAs

5.0  Escalation Communication Templates

6.0  Root Cause Analysis Process

7.0  Recurring Issue Patterns

8.0  Informatica Support Ticket Process

9.0  War Room Procedures for P1 Issues

# Prerequisites & Applicability

Issue tracking tool configured (Jira, ServiceNow, or equivalent)

Team roles and contact information documented

Informatica support contract and portal access confirmed

Communication channels established (Teams, email DLs, bridge lines)

# 1. Issue Management Lifecycle

The issue management lifecycle follows five stages. Every issue must progress through each stage with documented status transitions and timestamps.

## 1.1 Lifecycle Stages

| Stage | Description | Owner | Output |
| --- | --- | --- | --- |
| Identify | Issue detected or reported by any team member | Reporter | Issue ticket created |
| Classify | Severity and priority assigned based on impact | PM / Tech Lead | Severity rating (P1-P4) |
| Assign | Issue routed to the appropriate resolver | PM | Assigned owner + target date |
| Resolve | Root cause identified and fix implemented | Assigned Owner | Resolution details documented |
| Close | Resolution verified and issue formally closed | PM / Reporter | Closure confirmation + lessons learned |

## 1.2 Issue Ticket Fields

Issue ID (auto-generated)

Title and detailed description

Date reported and reporter name

Severity (P1/P2/P3/P4) and priority ranking

Affected component (mapping, connector, environment, data)

Assigned owner and target resolution date

Status (Open / In Progress / Pending / Resolved / Closed)

Resolution notes and root cause category

# 2. Severity Classification

Issues are classified into four severity levels based on business impact and scope of disruption. Severity drives the response time SLA and escalation path.

| Severity | Name | Definition | Business Impact | Examples |
| --- | --- | --- | --- | --- |
| P1 | Critical | Production down or data integrity compromised | Revenue / compliance impact | Pipeline failure losing customer data; production environment unresponsive |
| P2 | High | Major functionality impaired, workaround exists | Significant operational disruption | Key mapping failing intermittently; data latency exceeding SLA by 2x |
| P3 | Medium | Minor functionality impacted, no workaround urgently needed | Limited operational impact | Non-critical report delayed; minor data quality issue in one field |
| P4 | Low | Cosmetic or minor inconvenience | Minimal or no impact | Dashboard formatting issue; documentation error; enhancement request |

CRITICAL

Severity classification must be applied within 30 minutes of issue identification. When in doubt, assign a higher severity; it can be downgraded after initial assessment.

# 3. Escalation Matrix

The escalation matrix defines who must be notified and engaged at each severity level and escalation tier. Escalation is time-bound: if resolution is not achieved within the defined SLA, automatic escalation occurs.

| Escalation Level | Triggered When | Notified Parties | Decision Authority |
| --- | --- | --- | --- |
| Level 0 - Team | Issue identified | Team Lead, Assigned Owner | Tech Lead |
| Level 1 - Management | SLA 50% elapsed without resolution | PM, Delivery Manager | PM |
| Level 2 - Leadership | SLA 80% elapsed or P1 not resolved in 2 hrs | Program Director, Client Lead | Program Director |
| Level 3 - Executive | SLA breached or client-impacting P1 | VP Delivery, Client Executive | VP / Executive Sponsor |

## 3.1 Informatica-Specific Escalation

For issues requiring Informatica vendor support, follow the parallel escalation path:

Open a support ticket via the Informatica Support Portal (see Section 8).

Assign severity matching the internal classification.

Request TAM (Technical Account Manager) engagement for P1 issues.

Escalate to Informatica management if vendor SLA is at risk.

# 4. Response Time SLAs

Response time SLAs define the maximum acceptable time for initial response, status update frequency, and resolution targets for each severity level.

| Severity | Initial Response | Status Update Frequency | Resolution Target | Escalation Trigger |
| --- | --- | --- | --- | --- |
| P1 - Critical | 15 minutes | Every 30 minutes | 4 hours | 2 hours without progress |
| P2 - High | 1 hour | Every 2 hours | 8 business hours | 4 hours without progress |
| P3 - Medium | 4 business hours | Daily | 3 business days | 2 days without progress |
| P4 - Low | 1 business day | Weekly | 10 business days | 5 days without progress |

INFO

SLA timers are measured in business hours (Mon-Fri, 8am-6pm local time) except for P1 issues which use 24/7 clock time. Ensure on-call rotations cover P1 response outside business hours.

# 5. Escalation Communication Templates

Standardized communication templates ensure consistent, complete, and professional escalation notifications. Use these templates for all escalation communications.

## 5.1 Initial Notification Template

Subject: [SEVERITY] Issue Escalation - [Brief Description]

Issue ID:       [ISS-XXXX]

Severity:       [P1/P2/P3/P4]

Reported:       [Date/Time]

Escalation Lvl: [Level 1/2/3]

Description:

[Concise description of the issue and observed behavior]

Business Impact:

[How this affects operations, data, or users]

Current Status:

[Actions taken so far and current state]

Requested Action:

[What is needed from the escalation recipient]

Next Update: [Date/Time]

## 5.2 Status Update Template

Subject: UPDATE - [SEVERITY] [Issue ID] - [Brief Description]

Status:     [Investigating / Identified / Implementing Fix / Monitoring]

Progress:   [What has happened since the last update]

Next Steps: [Planned actions and expected timeline]

ETA:        [Estimated time to resolution]

Risks:      [Any factors that may delay resolution]

# 6. Root Cause Analysis Process

Root cause analysis (RCA) is mandatory for all P1 and P2 issues and recommended for recurring P3 issues. The RCA must be completed within 5 business days of issue closure.

## 6.1 RCA Methodology

Use the 5-Whys technique combined with an Ishikawa (fishbone) diagram to systematically identify root causes across six categories:

People - Skills gaps, training needs, communication failures

Process - Missing or inadequate procedures, workflow gaps

Technology - Platform bugs, configuration errors, capacity limits

Data - Data quality issues, schema changes, volume spikes

Environment - Infrastructure failures, network issues, access problems

External - Vendor issues, third-party dependencies, regulatory changes

## 6.2 RCA Report Template

| Section | Content |
| --- | --- |
| Issue Summary | Brief description, severity, duration, impact |
| Timeline | Chronological sequence of events |
| Root Cause | Primary and contributing causes identified |
| Impact Analysis | Business and technical impact quantified |
| Corrective Actions | Immediate fixes applied |
| Preventive Actions | Changes to prevent recurrence |
| Owner & Due Date | Responsible person and timeline for each action |

# 7. Recurring Issue Patterns

Analyzing issue patterns helps identify systemic problems. Track these common recurring issue categories in Informatica IDMC programs:

| Pattern | Typical Root Cause | Prevention Strategy |
| --- | --- | --- |
| Connection timeouts | Network instability or source system overload | Connection pooling, retry logic, health checks |
| Mapping failures after source schema change | No change notification from source team | Schema drift detection, CDC monitoring |
| IPU spikes on specific days | Large batch jobs scheduled concurrently | Stagger scheduling, optimize heavy mappings |
| Data quality rule failures | Upstream data format changes | Input validation, profiling alerts |
| Session concurrency limits | Too many parallel taskflows | Capacity planning, queue management |
| Deployment failures | Environment configuration drift | IaC templates, environment parity checks |

BEST PRACTICE

Conduct a monthly issue trend review. If the same root cause category accounts for more than 30% of issues, prioritize a systemic fix over continued firefighting.

# 8. Informatica Support Ticket Process

When issues require Informatica vendor assistance, follow this standardized process to ensure efficient resolution through Informatica Global Customer Support.

## 8.1 Ticket Submission Steps

Log in to the Informatica Support Portal (https://support.informatica.com).

Select 'Create Case' and choose the appropriate product (IICS, CDI, DQ, etc.).

Set severity matching internal classification (map P1-P4 to Informatica S1-S4).

Provide detailed reproduction steps, error messages, and session logs.

Attach relevant exports: mapping XML, session logs, IDMC audit logs.

Specify business impact and urgency clearly in the description.

## 8.2 Informatica Severity Mapping

| Internal Severity | Informatica Severity | Informatica SLA |
| --- | --- | --- |
| P1 - Critical | S1 - Production Outage | 1 hour initial response, continuous engagement |
| P2 - High | S2 - Significant Impact | 2 hour initial response, 4-hour updates |
| P3 - Medium | S3 - Moderate Impact | 4 business hours initial response |
| P4 - Low | S4 - Minor Impact | 1 business day initial response |

# 9. War Room Procedures for P1 Issues

P1 issues require an immediate war room response to coordinate resolution efforts. The war room remains active until the issue is resolved or a stable workaround is implemented.

## 9.1 War Room Activation

PM or Tech Lead declares a war room within 15 minutes of P1 classification.

Bridge line / Teams meeting is opened and shared with all required participants.

Incident Commander is designated (typically the Tech Lead or Senior Architect).

Scribe is assigned to document all actions and decisions in real-time.

## 9.2 War Room Roles

| Role | Responsibility | Typical Assignee |
| --- | --- | --- |
| Incident Commander | Leads investigation and decision-making | Tech Lead / Sr. Architect |
| Scribe | Documents timeline, actions, and decisions | Business Analyst / Jr. PM |
| Technical SMEs | Investigate root cause and implement fix | Developers, DBAs, Infra |
| Communication Lead | Provides updates to stakeholders | Program Manager |
| Vendor Liaison | Manages Informatica support engagement | Designated support contact |

## 9.3 War Room Exit Criteria

Issue resolved and verified in production, OR

Stable workaround implemented and approved by business owner

Monitoring confirmed for at least one full business cycle

RCA initiated with owner and due date assigned

All-clear communication sent to stakeholders

WARNING

War rooms must have a single Incident Commander with clear authority. Parallel investigations without coordination lead to longer resolution times and conflicting actions.

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| GOV_Scope_Change_Control_Process.docx | Governance Library |
| GOV_Stakeholder_Communication_Plan.docx | Governance Library |
| GOV_Status_Reporting_Templates.docx | Governance Library |
| PM_Risk_Management_Plan.docx | Project Management |
| OPS_Monitoring_Alerting_Guide.docx | Operations |