# Program Metrics & KPIs

Mastech Digital — Informatica Platform Assets

Comprehensive metrics framework and KPI catalog for Informatica IDMC program governance.

| Document | Program Metrics & KPIs |
| --- | --- |
| Category | Governance Library |
| Document ID | #53 |
| Version | 1.0 |
| Date | February 2026 |
| Author | Mastech Digital — Informatica Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Informatica IDMC (IICS) – Early 2026 |
| Next Review | August 2026 |

# Executive Summary

Effective program governance requires measurable indicators that objectively track delivery health, quality outcomes, adoption rates, and business value realization. This document defines the metrics framework, KPI catalog, measurement methodology, and reporting cadence for Informatica IDMC implementation programs. It provides standardized dashboards and benchmarks to enable data-driven decision-making across all program phases.

# Table of Contents

1.0  Metrics Framework Overview

2.0  Delivery KPIs

3.0  Quality KPIs

4.0  Adoption KPIs

5.0  Value Realization KPIs

6.0  Measurement Methodology

7.0  Dashboard Design

8.0  Reporting Cadence

9.0  Benchmarking & Targets

10.0  Data Quality Metrics

11.0  IPU Utilization Metrics

12.0  Time-to-Value Tracking

# Prerequisites & Applicability

Program charter and scope baseline approved

IDMC environment provisioned with monitoring access

IPU allocation documented and budgeted

Stakeholder agreement on KPI definitions and targets

Reporting tooling available (Power BI, Tableau, or IICS dashboards)

# 1. Metrics Framework Overview

The metrics framework organizes program indicators into four pillars: Delivery, Quality, Adoption, and Value. Each pillar contains specific KPIs with defined measurement methods, data sources, targets, and reporting frequencies.

## 1.1 Framework Pillars

| Pillar | Focus Area | Primary Audience | Cadence |
| --- | --- | --- | --- |
| Delivery | Schedule, scope, budget adherence | PMO, Steering Committee | Weekly |
| Quality | Defect rates, test coverage, SLA compliance | Technical Leads, QA | Weekly/Sprint |
| Adoption | User onboarding, feature utilization | Business Sponsors, Change Mgmt | Monthly |
| Value | ROI, cost savings, business outcomes | Executive Sponsors, Finance | Quarterly |

## 1.2 KPI Maturity Model

Programs should progress through three maturity levels of metrics adoption:

Level 1 (Foundation) - Track delivery and quality basics: schedule variance, defect counts, test pass rates.

Level 2 (Managed) - Add adoption and efficiency metrics: user onboarding velocity, pipeline throughput, IPU consumption trends.

Level 3 (Optimized) - Full value tracking with predictive analytics: time-to-value, cost-per-integration, ROI realization curves.

BEST PRACTICE

Start with 8-10 core KPIs in Level 1. Avoid metric overload; each KPI must have a clear owner and action trigger.

# 2. Delivery KPIs

Delivery KPIs measure how well the program adheres to committed timelines, scope, and budget. These are the most commonly tracked metrics in steering committee reviews.

| KPI | Formula | Target | Source |
| --- | --- | --- | --- |
| Schedule Performance Index (SPI) | Earned Value / Planned Value | >= 0.95 | Project plan / Jira |
| Cost Performance Index (CPI) | Earned Value / Actual Cost | >= 0.95 | Financial tracker |
| Sprint Velocity | Story points completed per sprint | Within 10% of avg | Jira / ADO |
| Milestone Completion Rate | Milestones on-time / Total milestones | >= 90% | Project plan |
| Scope Change Rate | Approved CRs / Original scope items | < 15% | Change log |
| Resource Utilization | Billable hours / Available hours | 80-90% | Timesheet system |

## 2.1 Schedule Variance Tracking

Track schedule variance at both the milestone and task level. A negative SV indicates the program is behind schedule. Aggregate SV by workstream to identify bottlenecks.

Green: SPI >= 0.95 and all critical-path milestones on track

Amber: SPI 0.85-0.94 or one critical-path milestone at risk

Red: SPI < 0.85 or critical-path milestone missed

# 3. Quality KPIs

Quality KPIs ensure that delivered integrations, mappings, and data assets meet defined standards and pass validation gates before promotion to production.

| KPI | Formula | Target | Source |
| --- | --- | --- | --- |
| Defect Density | Defects found / Mappings delivered | < 0.3 per mapping | Defect tracker |
| Test Pass Rate | Tests passed / Tests executed | >= 95% | Test management tool |
| Code Review Coverage | Reviewed assets / Total assets | 100% | Git / review tool |
| Production Incident Rate | P1-P2 incidents / Month | < 2 per month | ITSM tool |
| First-Time Pass Rate | Deployments without rollback / Total | >= 90% | CI/CD pipeline |
| Data Validation Score | Clean records / Total records processed | >= 99.5% | IDMC monitoring |

WARNING

Quality KPIs must be baselined during the first two sprints. Setting unrealistic targets leads to gaming metrics rather than genuine quality improvement.

# 4. Adoption KPIs

Adoption KPIs measure how effectively stakeholders and end users embrace the Informatica platform, features, and new processes introduced by the program.

| KPI | Formula | Target | Source |
| --- | --- | --- | --- |
| User Onboarding Rate | Active users / Licensed users | >= 80% by Go-Live +60d | IDMC admin console |
| Feature Utilization | Features used / Features available | >= 60% | IDMC usage analytics |
| Training Completion | Users trained / Target audience | >= 95% | LMS / training tracker |
| Self-Service Ratio | Self-service tasks / Total tasks | >= 40% by Year 1 | Service desk |
| Support Ticket Trend | Monthly ticket volume (declining) | 20% reduction QoQ | ITSM tool |

## 4.1 Adoption Curve Benchmarks

Typical IDMC adoption follows a phased curve. The first 90 days post go-live are critical for establishing usage patterns. Plan hypercare support and targeted communication to drive adoption during this window.

# 5. Value Realization KPIs

Value KPIs connect program outputs to business outcomes. These are the ultimate measures of program success and are typically reviewed quarterly with executive sponsors.

| KPI | Formula | Target | Source |
| --- | --- | --- | --- |
| Cost Savings Realized | Manual cost avoided via automation | Per business case | Finance |
| Time Saved (FTE hours) | Hrs/month saved by automation | Per business case | Process analysis |
| Data Availability SLA | Uptime of critical data pipelines | >= 99.5% | IDMC monitoring |
| Revenue Impact | Revenue enabled by data integration | Per business case | Business sponsor |
| Compliance Score | Audit findings addressed / Total | 100% | Audit / GRC tool |

INFO

Value KPIs require baseline measurements before the program starts. Work with Finance and business sponsors to establish current-state cost and time benchmarks.

# 6. Measurement Methodology

Consistent measurement methodology ensures KPI data is reliable, comparable, and actionable. Each KPI must have a documented measurement specification.

## 6.1 KPI Specification Template

| Attribute | Description |
| --- | --- |
| KPI Name | Clear, unambiguous name |
| Definition | Precise calculation formula |
| Data Source | System or tool providing raw data |
| Collection Frequency | How often data is gathered |
| Owner | Person responsible for data accuracy |
| Target / Threshold | Green / Amber / Red thresholds |
| Action Trigger | What happens when threshold is breached |

## 6.2 Data Collection Approaches

Automated extraction from IDMC APIs and monitoring dashboards

Manual collection via surveys, timesheets, and self-reporting

Hybrid approach with automated data validated by manual review

# 7. Dashboard Design

Program dashboards provide real-time visibility into KPI performance. Design dashboards for three distinct audiences: executive, management, and technical.

## 7.1 Executive Dashboard

RAG status for each pillar (Delivery, Quality, Adoption, Value)

Top 3 risks and issues with mitigation status

Budget burn-down and forecast

Key milestone timeline with actuals vs. planned

## 7.2 Management Dashboard

Sprint velocity and burn-down charts

Defect aging and resolution trend

Resource allocation and utilization heat map

Change request backlog and approval pipeline

## 7.3 Technical Dashboard

Pipeline execution success/failure rates

IPU consumption by service and mapping

Data quality scores by domain

Environment health and connectivity status

# 8. Reporting Cadence

| Report | Audience | Frequency | Owner | Format |
| --- | --- | --- | --- | --- |
| Daily Stand-up Metrics | Scrum Team | Daily | Scrum Master | Verbal + board |
| Sprint Report | Delivery Team | Bi-weekly | Tech Lead | Slide deck |
| Weekly Status Report | PMO / Sponsors | Weekly | PM | Document / email |
| Monthly Executive Report | Steering Committee | Monthly | Program Director | Slide deck |
| Quarterly Business Review | Executives | Quarterly | Program Director | Executive brief |

Each report should reference the same underlying KPI data to ensure consistency. Automate data pipelines from source systems into the reporting layer to reduce manual effort and improve accuracy.

# 9. Benchmarking & Targets

Benchmarks provide context for KPI performance by comparing against industry standards, historical performance, and peer programs. Targets should be set collaboratively with stakeholders using SMART criteria.

## 9.1 Industry Benchmarks

| Metric | Industry Average | Top Quartile | Mastech Target |
| --- | --- | --- | --- |
| Sprint Velocity Variance | +/- 20% | +/- 10% | +/- 10% |
| Defect Density | 0.5 per deliverable | 0.2 per deliverable | < 0.3 |
| Production Incident Rate | 5 per month | 1 per month | < 2 |
| User Adoption at Go-Live +90d | 60% | 85% | >= 80% |

BEST PRACTICE

Re-baseline targets at each phase gate. Targets set during planning may need adjustment as the team gains velocity and learns the platform.

# 10. Data Quality Metrics

Data quality is a critical dimension for Informatica programs. IDMC provides built-in data profiling and quality scoring capabilities that should feed directly into program KPIs.

| Dimension | Metric | Target | IDMC Feature |
| --- | --- | --- | --- |
| Completeness | % of non-null required fields | >= 99% | Data Quality rules |
| Accuracy | % of records matching golden source | >= 98% | Data Quality scorecards |
| Consistency | % of records with uniform formats | >= 99% | Data Quality standardization |
| Timeliness | Data freshness (lag from source) | < 15 min for real-time | CDI / streaming |
| Uniqueness | % of records without duplicates | >= 99.5% | CDI match/merge |

# 11. IPU Utilization Metrics

IPU (Informatica Processing Unit) consumption is the primary cost driver for IDMC. Tracking IPU usage by service, mapping, and business unit enables cost optimization and accurate forecasting.

## 11.1 IPU Tracking KPIs

| KPI | Formula | Target |
| --- | --- | --- |
| IPU Burn Rate | IPUs consumed / Time period | Within 90% of forecast |
| IPU per Mapping | IPUs consumed / Mapping executions | Declining trend |
| IPU Budget Variance | (Actual - Budget) / Budget | +/- 10% |
| Peak IPU Utilization | Max hourly IPU / Allocated IPU | < 85% |
| IPU by Service | IPU by CDI, DQ, Mass Ingestion, etc. | Per allocation plan |

WARNING

Monitor IPU consumption daily during initial deployment. Unexpected spikes can exhaust annual allocations within weeks if complex mappings run without optimization.

# 12. Time-to-Value Tracking

Time-to-Value (TTV) measures the elapsed time from project initiation to the point where measurable business value is realized. Shorter TTV indicates better program execution and stakeholder alignment.

## 12.1 TTV Milestones

| Milestone | Typical TTV | Accelerated TTV | Enabler |
| --- | --- | --- | --- |
| First mapping in production | 6-8 weeks | 3-4 weeks | Pre-built templates |
| First data quality dashboard | 8-10 weeks | 4-6 weeks | IDMC DQ accelerators |
| First business report from IDMC data | 10-12 weeks | 6-8 weeks | Agile delivery |
| Full pipeline portfolio live | 16-24 weeks | 10-16 weeks | Phased rollout |
| Positive ROI demonstrated | 6-9 months | 4-6 months | Quick wins strategy |

## 12.2 Accelerating Time-to-Value

Prioritize high-impact, low-complexity use cases for early delivery

Use Informatica pre-built connectors and templates to reduce development time

Implement CI/CD pipelines early to accelerate deployment cycles

Establish a reusable asset library from day one

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| GOV_Scope_Change_Control_Process.docx | Governance Library |
| GOV_Status_Reporting_Templates.docx | Governance Library |
| GOV_Stakeholder_Communication_Plan.docx | Governance Library |
| PM_Budget_IPU_Forecasting.docx | Project Management |
| TA_IDMC_Performance_Tuning_Guide.docx | Technical Architecture |