# Project Governance Framework

Mastech Digital — Informatica Platform Assets

Defines the governance structure, decision-making authority, and oversight cadence for Informatica IDMC implementation projects.

| Document | Project Governance Framework |
| --- | --- |
| Category | Governance Library |
| Document ID | #48 |
| Version | 1.0 |
| Date | February 2026 |
| Author | Mastech Digital — Informatica Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Informatica IDMC (IICS) – Early 2026 |
| Next Review | August 2026 |

# Executive Summary

This document establishes the governance framework for Informatica IDMC projects at Mastech Digital. It defines roles, responsibilities, decision-making authority, steering committee operations, escalation paths, and gate reviews that ensure projects are delivered on time, within scope, and aligned to business objectives. A robust governance model reduces risk, improves stakeholder confidence, and provides clear accountability at every phase of the project lifecycle.

# Table of Contents

1.0  Governance Structure

2.0  RACI Matrix

3.0  Decision-Making Authority

4.0  Steering Committee Charter

5.0  Governance Cadence

6.0  Escalation Paths

7.0  Gate Reviews

8.0  Compliance Checkpoints

9.0  Stakeholder Roles

10.0  Governance Tools & Templates

# Prerequisites & Applicability

Project charter or statement of work (SOW) approved

IDMC organization and sub-organization provisioned

Stakeholder list identified and confirmed

Access to project management tooling (Jira, Azure DevOps, or equivalent)

# 1. Governance Structure

The governance structure for Informatica IDMC projects follows a three-tier model designed to provide strategic oversight, tactical management, and operational execution accountability.

## 1.1 Three-Tier Governance Model

| Tier | Body | Frequency | Focus |
| --- | --- | --- | --- |
| Strategic | Steering Committee | Monthly | Portfolio alignment, risk escalation, funding decisions |
| Tactical | Project Management Office | Biweekly | Scope, schedule, budget tracking, cross-project dependencies |
| Operational | Delivery Team Leads | Weekly / Daily | Sprint execution, technical decisions, impediment removal |

Each tier has defined authority boundaries. Decisions that exceed the authority of a given tier are escalated upward through predefined channels.

BEST PRACTICE

Establish the governance structure during project kickoff and document it in the project charter. All stakeholders should acknowledge the governance model before development begins.

# 2. RACI Matrix

The RACI matrix clarifies who is Responsible, Accountable, Consulted, and Informed for each key project activity. This eliminates ambiguity and prevents both gaps and overlaps in ownership.

| Activity | Sponsor | PM | Tech Lead | Developer | QA | Business SME |
| --- | --- | --- | --- | --- | --- | --- |
| Requirements Sign-off | A | R | C | I | I | C |
| Architecture Design | I | C | A/R | C | I | I |
| Mapping Development | I | I | C | A/R | I | C |
| Test Strategy | I | C | C | I | A/R | C |
| UAT Approval | A | R | I | I | C | R |
| Production Deployment | A | R | R | C | C | I |
| Change Requests | A | R | C | I | I | C |
| Risk Escalation | A | R | C | I | I | I |

R = Responsible | A = Accountable | C = Consulted | I = Informed

# 3. Decision-Making Authority

Clear decision-making authority prevents bottlenecks and ensures timely resolution of project issues. Authority is delegated based on the impact and scope of the decision.

| Decision Type | Authority Level | Approval Required | Turnaround SLA |
| --- | --- | --- | --- |
| Technical design choices | Tech Lead | No | Same day |
| Minor scope adjustments (<5% effort) | Project Manager | PM approval | 2 business days |
| Major scope changes (>5% effort) | Steering Committee | Sponsor + PM | 1 week |
| Budget reallocation | Steering Committee | Sponsor | 1 week |
| Timeline extension | PMO + Sponsor | Sponsor | 3 business days |
| Vendor/tool changes | Steering Committee | Sponsor + CTO | 2 weeks |

WARNING

Decisions made outside the delegated authority matrix may be reversed by the steering committee. Always verify the authority level before committing to changes.

# 4. Steering Committee Charter

The Steering Committee provides strategic oversight and is the highest escalation point for the project. It ensures alignment between the project and business objectives.

## 4.1 Composition

Executive Sponsor (Chair)

Business Unit Leader(s)

IT Director / CTO Representative

Program Manager

Informatica Practice Lead (Mastech Digital)

## 4.2 Responsibilities

Approve major scope changes and budget reallocations

Resolve cross-functional conflicts and escalations

Review and accept gate review outcomes

Provide strategic direction on project priorities

Authorize production go-live decisions

## 4.3 Meeting Protocol

Cadence: Monthly (ad hoc meetings for critical escalations)

Quorum: At least 3 of 5 members including the Sponsor

Agenda distributed 3 business days prior to meeting

Minutes published within 2 business days after meeting

Action items tracked in project management tool

# 5. Governance Cadence

Regular governance touchpoints ensure the project remains on track and issues are identified early. The cadence aligns with agile sprint cycles.

| Meeting | Cadence | Attendees | Purpose |
| --- | --- | --- | --- |
| Daily Standup | Daily | Delivery team | Progress updates, impediment flagging |
| Sprint Review/Demo | Biweekly | Team + stakeholders | Demonstrate completed work, gather feedback |
| Sprint Retrospective | Biweekly | Delivery team | Process improvement |
| PMO Status Review | Biweekly | PM + PMO | Budget, schedule, risk review |
| Steering Committee | Monthly | Steering members | Strategic oversight, escalation resolution |
| Gate Review | Per phase | PM + Tech Lead + QA | Phase transition approval |

INFO

For smaller projects (under 3 months), the PMO status review and steering committee meetings may be combined into a single monthly governance session.

# 6. Escalation Paths

Escalation paths provide a structured mechanism to raise issues that cannot be resolved at the current authority level. Timely escalation prevents small issues from becoming project-threatening problems.

## 6.1 Escalation Tiers

| Level | Escalated To | Trigger | Response SLA |
| --- | --- | --- | --- |
| L1 | Tech Lead / Scrum Master | Technical blocker or team conflict | 4 hours |
| L2 | Project Manager | Schedule impact > 2 days or resource constraint | 1 business day |
| L3 | PMO / Program Manager | Budget impact or cross-project dependency | 2 business days |
| L4 | Steering Committee / Sponsor | Scope change, strategic risk, or vendor issue | 1 week |

## 6.2 Escalation Procedure

Document the issue with impact assessment and proposed resolution options

Notify the next-level authority via email and project management tool

Schedule a resolution meeting within the SLA window

Document the decision and communicate to all affected parties

Track resolution as an action item until closed

# 7. Gate Reviews

Gate reviews are formal checkpoints that validate project readiness to transition between phases. Each gate has defined entry and exit criteria that must be satisfied before proceeding.

| Gate | Phase Transition | Key Criteria |
| --- | --- | --- |
| G0 | Initiation -> Requirements | Charter approved, team staffed, environments requested |
| G1 | Requirements -> Design | Requirements signed off, scope baseline approved |
| G2 | Design -> Build | Architecture reviewed, design documents approved |
| G3 | Build -> Test | Code complete, unit tests passed, peer review done |
| G4 | Test -> UAT | System tests passed, defect backlog acceptable |
| G5 | UAT -> Production | UAT signed off, deployment runbook approved, rollback plan validated |

CRITICAL

No phase transition may occur without formal gate approval. Bypassing gates requires written Steering Committee authorization and risk acceptance.

# 8. Compliance Checkpoints

Compliance checkpoints ensure the project adheres to organizational policies, regulatory requirements, and Informatica platform best practices.

Data Privacy: Verify PII handling aligns with GDPR/CCPA requirements at G1 and G5

Security: Validate connection credentials use Secure Agent vault, not hardcoded values

Licensing: Confirm IPU consumption projections against contracted capacity

Audit Trail: Ensure all design decisions and change requests are documented

Source Control: Verify all exportable assets are committed to Git repository

Naming Standards: Validate all assets follow the organizational naming convention

# 9. Stakeholder Roles

Clear stakeholder role definitions prevent confusion and ensure effective collaboration across teams.

| Role | Responsibilities | Time Commitment |
| --- | --- | --- |
| Executive Sponsor | Strategic direction, funding approval, escalation resolution | 5-10% |
| Business SME | Requirements validation, UAT execution, data knowledge | 25-50% |
| Project Manager | Planning, tracking, reporting, risk management, stakeholder communication | 100% |
| Technical Lead | Architecture, design decisions, code reviews, technical mentoring | 80-100% |
| Developer | Mapping development, unit testing, documentation | 100% |
| QA Engineer | Test planning, execution, defect management | 100% during test phases |
| Release Manager | Deployment coordination, environment management, promotion | As needed |

# 10. Governance Tools & Templates

The following tools and templates support governance activities throughout the project lifecycle.

## 10.1 Recommended Tools

| Tool Category | Recommended Options | Purpose |
| --- | --- | --- |
| Project Management | Jira, Azure DevOps, Smartsheet | Sprint tracking, backlog management |
| Source Control | GitHub, Azure Repos, Bitbucket | Version control for IICS assets |
| Documentation | Confluence, SharePoint | Design documents, runbooks, meeting notes |
| Communication | Teams, Slack | Daily standups, escalation channels |
| Monitoring | IDMC Operations Console, Datadog | Job monitoring, SLA tracking |

## 10.2 Governance Templates

Project Charter Template

RACI Matrix Template

Gate Review Checklist

Steering Committee Agenda Template

Escalation Log Template

Risk Register Template

Status Report Template (weekly/biweekly)

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| Quality Gates & Checkpoints | Governance_Library / #49 |
| Risk Management Playbook | Governance_Library / #50 |
| CI/CD & Environment Promotion Guide | Governance_Library / #51 |
| Naming Standards Guide | Governance_Library / #52 |