# Quality Gates & Checkpoints

Mastech Digital — Informatica Platform Assets

Defines quality gate criteria, defect classification, and approval workflows for Informatica IDMC project delivery.

| Document | Quality Gates & Checkpoints |
| --- | --- |
| Category | Governance Library |
| Document ID | #49 |
| Version | 1.0 |
| Date | February 2026 |
| Author | Mastech Digital — Informatica Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Informatica IDMC (IICS) – Early 2026 |
| Next Review | August 2026 |

# Executive Summary

Quality gates are formal checkpoints that ensure each phase of the Informatica IDMC project meets predefined standards before progressing. This document defines the gate framework, entry and exit criteria for every phase, defect classification standards, quality metrics, and the approval workflow. Consistent application of quality gates reduces production defects, ensures stakeholder confidence, and provides an auditable trail of project quality decisions.

# Table of Contents

1.0  Quality Gate Framework

2.0  Gate Definitions

3.0  Entry & Exit Criteria

4.0  Gate Review Process

5.0  Defect Classification

6.0  Quality Metrics

7.0  Gate Approval Workflow

8.0  Automated Quality Checks

# Prerequisites & Applicability

Project governance framework established (see #48)

Test strategy document approved

Defect tracking tool configured (Jira, Azure DevOps, etc.)

# 1. Quality Gate Framework

The quality gate framework provides a structured approach to validating project readiness at each phase transition. Six gates align with the standard SDLC phases for Informatica IDMC implementations.

## 1.1 Gate Overview

| Gate ID | Gate Name | Phase Boundary | Gate Owner |
| --- | --- | --- | --- |
| G0 | Requirements Gate | Initiation -> Design | Business SME + PM |
| G1 | Design Gate | Design -> Build | Tech Lead + Architect |
| G2 | Build Gate | Build -> System Test | Tech Lead + Developer |
| G3 | Test Gate | System Test -> UAT | QA Lead + PM |
| G4 | Deploy Gate | UAT -> Production | Release Manager + PM |
| G5 | Operate Gate | Hypercare -> Steady State | Operations Lead |

BEST PRACTICE

Schedule gate reviews at least 3 business days before the planned phase transition to allow time for remediation if criteria are not met.

# 2. Gate Definitions

## 2.1 G0 - Requirements Gate

Validates that business requirements are complete, unambiguous, and traceable. Source-to-target mappings must be reviewed and signed off by business SMEs.

All functional and non-functional requirements documented

Source-to-target mapping specifications approved

Data profiling results reviewed and anomalies documented

Acceptance criteria defined for each requirement

## 2.2 G1 - Design Gate

Confirms that the technical design satisfies the requirements and follows IDMC platform best practices.

Architecture design document reviewed and approved

Connection and runtime environment design validated

Error handling and logging strategy defined

Performance benchmarks and SLAs established

## 2.3 G2 - Build Gate

Verifies that all mappings, taskflows, and components are developed, unit tested, and peer reviewed.

All mappings developed per design specifications

Unit tests executed with documented results

Code peer review completed and findings resolved

Assets committed to source control

## 2.4 G3 - Test Gate

Ensures system testing is complete and defect levels are within acceptable thresholds.

System integration tests executed and passed

No open Critical or High defects

Performance tests meet SLA targets

Test coverage meets minimum threshold (>90%)

## 2.5 G4 - Deploy Gate

Confirms UAT is complete, production readiness is verified, and deployment artifacts are prepared.

UAT sign-off obtained from business stakeholders

Deployment runbook reviewed and approved

Rollback procedure tested

Production environment validated

## 2.6 G5 - Operate Gate

Validates that hypercare is complete and the solution is stable for transition to steady-state operations.

No critical incidents during hypercare period (typically 2-4 weeks)

Knowledge transfer to operations team completed

Monitoring and alerting configured and validated

Operations runbook and support procedures documented

# 3. Entry & Exit Criteria

Each gate has explicit entry criteria (preconditions for starting the review) and exit criteria (conditions that must be met to pass the gate).

| Gate | Entry Criteria | Exit Criteria |
| --- | --- | --- |
| G0 Requirements | Requirements elicitation complete, data profiling done | Requirements signed off, traceability matrix created |
| G1 Design | Requirements baseline approved | Design doc approved, environment plan finalized |
| G2 Build | Design approved, dev environment ready | Code complete, unit tests pass, peer review done |
| G3 Test | Build gate passed, test environment provisioned | All tests pass, defect backlog acceptable |
| G4 Deploy | UAT sign-off, deployment artifacts ready | Production deployment successful, smoke tests pass |
| G5 Operate | Hypercare period started, monitoring active | Hypercare complete, operations handoff accepted |

WARNING

A gate cannot be entered if the previous gate's exit criteria have not been met. Any exceptions require documented risk acceptance from the project sponsor.

# 4. Gate Review Process

Gate reviews are formal meetings that evaluate whether all criteria for a phase transition have been satisfied.

## 4.1 Review Steps

Gate owner compiles evidence artifacts (test results, sign-offs, metrics)

Review package distributed to gate reviewers 3 business days in advance

Gate review meeting conducted with structured agenda

Outcome recorded: Pass, Conditional Pass (with action items), or Fail

Decision communicated to all stakeholders and logged in project tracker

## 4.2 Gate Review Outcomes

| Outcome | Definition | Action Required |
| --- | --- | --- |
| Pass | All criteria met | Proceed to next phase |
| Conditional Pass | Minor criteria gaps with mitigation plan | Address action items within agreed timeline |
| Fail | Critical criteria not met | Remediate and reschedule gate review |

# 5. Defect Classification

Consistent defect classification ensures appropriate prioritization and enables meaningful quality metrics across the project.

| Severity | Definition | Resolution SLA | Example |
| --- | --- | --- | --- |
| Critical | System unusable, data loss or corruption, no workaround | 4 hours | Mapping produces incorrect financial aggregations |
| High | Major feature broken, significant impact, workaround exists | 1 business day | Taskflow fails intermittently under load |
| Medium | Feature partially impaired, acceptable workaround available | 3 business days | Error handling logs insufficient detail |
| Low | Cosmetic or minor issue, minimal user impact | Next sprint | Field label mismatch in parameter file |

CRITICAL

All Critical and High defects must be resolved before passing G3 (Test Gate) and G4 (Deploy Gate). No exceptions without Steering Committee approval.

# 6. Quality Metrics

Quality metrics are tracked throughout the project to provide objective measures of project health and inform gate decisions.

| Metric | Target | Measured At | Owner |
| --- | --- | --- | --- |
| Requirements coverage | >95% mapped to test cases | G0, G3 | QA Lead |
| Unit test pass rate | 100% | G2 | Developer |
| System test pass rate | >95% | G3 | QA Lead |
| Defect leakage rate | <5% to UAT | G4 | QA Lead |
| Code review completion | 100% of mappings reviewed | G2 | Tech Lead |
| Performance SLA compliance | 100% within targets | G3 | Tech Lead |
| Deployment success rate | >99% | G4 | Release Manager |

# 7. Gate Approval Workflow

The approval workflow defines the sequence of reviews and sign-offs required to pass each quality gate.

## 7.1 Workflow Steps

Gate owner prepares gate package with all evidence artifacts

Technical reviewer validates completeness and accuracy

Gate review meeting conducted

Gate owner records outcome and action items

PM obtains required approvals (digital sign-off in project tracker)

Phase transition authorized and communicated

## 7.2 Approval Authority

| Gate | Required Approvers |
| --- | --- |
| G0 Requirements | Business SME, Project Manager |
| G1 Design | Tech Lead, Architect |
| G2 Build | Tech Lead, QA Lead |
| G3 Test | QA Lead, Project Manager |
| G4 Deploy | Release Manager, Project Manager, Business SME |
| G5 Operate | Operations Lead, Project Manager |

# 8. Automated Quality Checks

Automated checks supplement manual gate reviews to provide continuous quality validation throughout the development lifecycle.

## 8.1 Pre-Commit Checks

Naming convention validation against organizational standards

Connection parameter validation (no hardcoded credentials)

Asset completeness check (all referenced sub-components exist)

## 8.2 CI/CD Pipeline Checks

Automated export and import validation across environments

Regression test execution on promotion to TEST/UAT

IPU consumption estimation for new or modified mappings

Static analysis of mapping complexity and performance risks

INFO

Integrate automated quality checks into the CI/CD pipeline (see CI/CD & Environment Promotion Guide #51) so that gate criteria are continuously validated rather than checked only at gate reviews.

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| Project Governance Framework | Governance_Library / #48 |
| Risk Management Playbook | Governance_Library / #50 |
| CI/CD & Environment Promotion Guide | Governance_Library / #51 |
| Naming Standards Guide | Governance_Library / #52 |