# Risk Management Playbook

Mastech Digital — Informatica Platform Assets

Provides a comprehensive risk management framework for Informatica IDMC projects including identification, assessment, response planning, and monitoring.

| Document | Risk Management Playbook |
| --- | --- |
| Category | Governance Library |
| Document ID | #50 |
| Version | 1.0 |
| Date | February 2026 |
| Author | Mastech Digital — Informatica Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Informatica IDMC (IICS) – Early 2026 |
| Next Review | August 2026 |

# Executive Summary

Effective risk management is essential for successful Informatica IDMC project delivery. This playbook provides a structured approach to identifying, assessing, responding to, and monitoring risks throughout the project lifecycle. It includes risk categorization, probability-impact assessment, response strategies, a register template, and escalation triggers. Proactive risk management reduces surprises, protects project timelines, and ensures stakeholder confidence.

# Table of Contents

1.0  Risk Framework

2.0  Risk Identification Techniques

3.0  Risk Categorization

4.0  Probability-Impact Matrix

5.0  Risk Response Strategies

6.0  Risk Register Template

7.0  Risk Monitoring Cadence

8.0  Escalation Triggers

9.0  Contingency Planning

# Prerequisites & Applicability

Project governance framework in place (see #48)

Stakeholders identified and available for risk workshops

Risk tracking tool or register template available

# 1. Risk Framework

The risk management framework follows a continuous cycle of identification, assessment, response planning, monitoring, and communication. It is integrated into the project governance cadence so risks are reviewed regularly.

## 1.1 Risk Management Lifecycle

Identify: Discover and document potential risks

Assess: Evaluate probability and impact of each risk

Plan: Define response strategies and assign owners

Monitor: Track risk status and trigger indicators

Communicate: Report risk status to stakeholders per governance cadence

BEST PRACTICE

Begin risk identification during project initiation and maintain the risk register as a living document throughout the project lifecycle. Risks should be reviewed at every sprint retrospective and PMO status meeting.

# 2. Risk Identification Techniques

Multiple techniques should be used to ensure comprehensive risk identification. No single method captures all potential risks.

## 2.1 Techniques

| Technique | Description | When to Use |
| --- | --- | --- |
| Brainstorming Workshop | Structured team session to identify risks collaboratively | Project kickoff, phase transitions |
| Checklist Review | Review against common IDMC project risk checklist | Every gate review |
| SWOT Analysis | Analyze Strengths, Weaknesses, Opportunities, Threats | Project initiation |
| Lessons Learned Review | Examine risks from past IDMC projects | Project initiation, retrospectives |
| Expert Interviews | One-on-one discussions with SMEs and architects | Design and build phases |
| Assumption Analysis | Review project assumptions for hidden risks | Requirements and design phases |

## 2.2 Common IDMC Project Risks

Source system access delays or data quality issues

IPU consumption exceeding budget projections

Secure Agent infrastructure instability

Complex transformation logic causing performance bottlenecks

Dependency on IDMC platform updates or feature availability

Key resource attrition or availability constraints

# 3. Risk Categorization

Risks are categorized to enable structured analysis, pattern identification, and targeted response strategies.

| Category | Description | Examples |
| --- | --- | --- |
| Technical | Risks related to technology, architecture, or platform | IDMC API limitations, Secure Agent memory issues, complex transformations |
| Organizational | Risks related to people, processes, or governance | Resource turnover, stakeholder disengagement, unclear requirements |
| External | Risks from outside the project team's control | Vendor delays, regulatory changes, third-party system outages |
| Schedule | Risks that threaten project timeline | Environment provisioning delays, dependency on other projects, scope creep |

INFO

Tag every risk in the risk register with its category. This enables trend analysis and helps the team focus mitigation efforts where risks are concentrating.

# 4. Probability-Impact Matrix

The probability-impact matrix provides a standardized method for assessing risk severity. Each risk is scored on two dimensions and mapped to an overall risk rating.

## 4.1 Scoring Scales

| Score | Probability | Impact |
| --- | --- | --- |
| 1 - Very Low | <10% chance | Negligible impact on scope, schedule, or budget |
| 2 - Low | 10-25% chance | Minor impact, easily absorbed |
| 3 - Medium | 25-50% chance | Moderate impact, requires adjustment |
| 4 - High | 50-75% chance | Significant impact on deliverables |
| 5 - Very High | >75% chance | Severe impact, threatens project success |

## 4.2 Risk Rating Matrix

| Probability / Impact | 1 Very Low | 2 Low | 3 Medium | 4 High | 5 Very High |
| --- | --- | --- | --- | --- | --- |
| 5 Very High | 5 Medium | 10 High | 15 Critical | 20 Critical | 25 Critical |
| 4 High | 4 Low | 8 Medium | 12 High | 16 Critical | 20 Critical |
| 3 Medium | 3 Low | 6 Medium | 9 Medium | 12 High | 15 Critical |
| 2 Low | 2 Low | 4 Low | 6 Medium | 8 Medium | 10 High |
| 1 Very Low | 1 Low | 2 Low | 3 Low | 4 Low | 5 Medium |

WARNING

Risks rated Critical (score >= 15) must be escalated to the Steering Committee immediately. They require a dedicated mitigation plan with weekly status updates.

# 5. Risk Response Strategies

Every identified risk must have an assigned response strategy. The four standard strategies are Avoid, Mitigate, Transfer, and Accept.

| Strategy | Description | When to Use | Example |
| --- | --- | --- | --- |
| Avoid | Eliminate the risk by changing the approach | High probability + high impact risks | Choose proven mapping pattern instead of untested approach |
| Mitigate | Reduce probability or impact through actions | Medium-to-high risks with feasible countermeasures | Add performance testing early to detect bottlenecks |
| Transfer | Shift risk ownership to a third party | Risks better managed by another party | Use Informatica support for platform-specific issues |
| Accept | Acknowledge risk and monitor without active response | Low-rated risks or when mitigation cost exceeds impact | Accept minor UI inconsistencies in non-critical dashboards |

## 5.1 Response Planning Guidelines

Every risk rated Medium or above must have an active response strategy (Avoid, Mitigate, or Transfer)

Low-rated risks may be Accepted but must still be monitored

Response plans must include specific actions, owners, and target dates

Contingency plans should be defined for all High and Critical risks

# 6. Risk Register Template

The risk register is the central repository for all identified risks. It must be maintained throughout the project and reviewed at every governance meeting.

| Field | Description |
| --- | --- |
| Risk ID | Unique identifier (e.g., R-001) |
| Title | Brief descriptive title |
| Category | Technical / Organizational / External / Schedule |
| Description | Detailed description of the risk |
| Probability | Score 1-5 |
| Impact | Score 1-5 |
| Rating | Probability x Impact score |
| Response Strategy | Avoid / Mitigate / Transfer / Accept |
| Response Plan | Specific actions to execute the strategy |
| Owner | Person responsible for managing the risk |
| Status | Open / In Progress / Mitigated / Closed |
| Target Date | Date by which response actions should be completed |
| Trigger Indicator | Observable event that signals risk is materializing |

## 6.1 Sample Risk Register Entry

Risk ID:      R-003

Title:        IPU Consumption Exceeds Budget

Category:     Technical

Description:  Complex transformations in the Customer 360 domain may

consume more IPUs than estimated, exceeding the contracted

capacity by the end of Q3.

Probability:  3 (Medium)    Impact: 4 (High)    Rating: 12 (High)

Strategy:     Mitigate

Response:     1. Implement IPU monitoring dashboards

2. Optimize top-10 mappings by consumption

3. Establish IPU consumption review in sprint demos

Owner:        Tech Lead

Status:       In Progress

Target Date:  2026-04-15

Trigger:      Monthly IPU consumption > 80% of budget allocation

# 7. Risk Monitoring Cadence

Risk monitoring is integrated into the governance cadence to ensure risks are reviewed and updated regularly.

| Activity | Cadence | Participants | Output |
| --- | --- | --- | --- |
| Risk register review | Biweekly (sprint boundary) | PM, Tech Lead, QA Lead | Updated risk register |
| Risk status in PMO report | Biweekly | PM, PMO | Top-5 risks highlighted in status report |
| Critical risk escalation | As needed (within SLA) | PM, Steering Committee | Escalation report and mitigation plan |
| Risk retrospective | Monthly / phase transition | Full team | New risks identified, closed risks archived |

# 8. Escalation Triggers

Escalation triggers define the conditions under which a risk must be elevated to a higher governance tier for attention and decision-making.

| Trigger Condition | Escalation Level | Action |
| --- | --- | --- |
| Risk rating increases to Critical (>=15) | Steering Committee | Immediate notification, mitigation plan within 48 hours |
| Risk response actions overdue by > 1 week | PMO / Program Manager | Review blockers, reassign or escalate further |
| New risk identified with no feasible mitigation | PM + Sponsor | Risk acceptance decision required |
| Multiple risks materializing simultaneously | Steering Committee | Emergency review session, potential scope/timeline adjustment |
| Risk impacts cross-project dependencies | PMO | Cross-project coordination meeting |

CRITICAL

Escalation triggers should be communicated to all team members so risks are flagged immediately rather than waiting for the next scheduled review.

# 9. Contingency Planning

Contingency plans are pre-defined response actions that are executed only if a risk materializes. They provide a ready-to-execute playbook that reduces response time during crisis situations.

## 9.1 Contingency Plan Structure

Trigger: The event or condition that activates the contingency plan

Actions: Specific steps to execute, in sequence

Owner: Person responsible for initiating the contingency response

Resources: Budget, tools, or personnel reserved for contingency execution

Communication: Stakeholders to notify and communication channels to use

## 9.2 Common Contingency Scenarios

| Scenario | Contingency Response |
| --- | --- |
| Secure Agent failure in production | Failover to secondary agent group, notify ops team, initiate incident management |
| Key developer leaves mid-project | Activate backup resource from bench, knowledge transfer from documentation |
| IPU budget exhaustion | Pause non-critical workloads, optimize top consumers, request budget extension |
| Source system unavailable for testing | Switch to mock data sources, reschedule integration tests |
| Critical defect found in production | Execute rollback procedure, activate war room, apply hotfix process |

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| Project Governance Framework | Governance_Library / #48 |
| Quality Gates & Checkpoints | Governance_Library / #49 |
| CI/CD & Environment Promotion Guide | Governance_Library / #51 |