# Status Reporting Templates

Mastech Digital — Informatica Platform Assets

Standardized reporting templates and guidance for Informatica IDMC program status communications.

| Document | Status Reporting Templates |
| --- | --- |
| Category | Governance Library |
| Document ID | #57 |
| Version | 1.0 |
| Date | February 2026 |
| Author | Mastech Digital — Informatica Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Informatica IDMC (IICS) – Early 2026 |
| Next Review | August 2026 |

# Executive Summary

Consistent, high-quality status reporting is the backbone of program transparency and stakeholder trust. This document provides ready-to-use templates for weekly status reports, monthly executive reports, phase completion reports, and sprint reviews. It includes guidance on RAG status definitions, metrics dashboards, burn-down chart interpretation, and automated reporting using IICS APIs to reduce manual effort and improve data accuracy.

# Table of Contents

1.0  Reporting Framework

2.0  Weekly Status Report Template

3.0  Monthly Executive Report Template

4.0  Phase Completion Report

5.0  Sprint Review Template

6.0  Metrics Dashboard Template

7.0  Burn-Down / Burn-Up Charts

8.0  Automated Reporting with IICS APIs

# Prerequisites & Applicability

Reporting cadence agreed with stakeholders

KPIs and metrics baselined (refer to GOV_Program_Metrics_KPIs.docx)

SharePoint or shared repository for report storage

IICS API access provisioned for automated data collection (optional)

# 1. Reporting Framework

The reporting framework establishes a layered approach where each report type serves a specific audience and cadence. Higher-level reports aggregate data from lower levels, ensuring consistency across all communications.

## 1.1 Report Hierarchy

| Report Level | Report Type | Audience | Cadence | Detail Level |
| --- | --- | --- | --- | --- |
| L1 - Operational | Daily stand-up notes | Scrum Team | Daily | Task-level |
| L2 - Tactical | Weekly status report | PM, Sponsors, Leads | Weekly | Workstream-level |
| L3 - Management | Monthly executive report | Steering Committee | Monthly | Program-level |
| L4 - Strategic | Quarterly business review | C-suite | Quarterly | Portfolio-level |

## 1.2 Reporting Principles

Single source of truth: All reports draw from the same underlying data

Timeliness: Reports delivered on schedule, every time

Accuracy: Data validated before publishing; corrections issued promptly

Actionability: Every report includes clear next steps or decisions needed

Brevity: Respect the audience's time; use appendices for detail

INFO

Automate as much reporting data as possible. Manual data collection introduces errors and consumes project team capacity that is better spent on delivery.

# 2. Weekly Status Report Template

The weekly status report is the most frequently used communication artifact. It provides a consistent snapshot of program health for program managers and sponsors.

## 2.1 Template Structure

SECTION A: Overall Status

| Dimension | Status (RAG) | Trend | Comment |
| --- | --- | --- | --- |
| Schedule | [G/A/R] | [Up/Flat/Down] | [One-line explanation] |
| Budget | [G/A/R] | [Up/Flat/Down] | [One-line explanation] |
| Quality | [G/A/R] | [Up/Flat/Down] | [One-line explanation] |
| Scope | [G/A/R] | [Up/Flat/Down] | [One-line explanation] |
| Resources | [G/A/R] | [Up/Flat/Down] | [One-line explanation] |

SECTION B: Key Accomplishments (This Week)

1. [Accomplishment description - quantify where possible]

2. [Accomplishment description]

3. [Accomplishment description]

SECTION C: Planned Activities (Next Week)

1. [Planned activity - include owner and target date]

2. [Planned activity]

3. [Planned activity]

SECTION D: Risks & Issues

| ID | Type | Description | Severity | Owner | Mitigation / Resolution | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | Risk | [Description] | H/M/L | [Name] | [Mitigation plan] | [Open/Mitigating/Closed] |
| I-001 | Issue | [Description] | P1-P4 | [Name] | [Resolution plan] | [Open/In Progress/Closed] |

SECTION E: Decisions Needed

1. [Decision description] - Needed by: [Date] - Decision maker: [Name]

2. [Decision description] - Needed by: [Date] - Decision maker: [Name]

# 3. Monthly Executive Report Template

The monthly executive report provides a strategic view of program progress for steering committee members and executive sponsors. It emphasizes outcomes and value over activities.

## 3.1 Executive Report Sections

| Section | Content | Format |
| --- | --- | --- |
| Executive Summary | One paragraph program health overview | Narrative |
| Milestone Tracker | Planned vs. actual milestone dates | Gantt / timeline visual |
| Financial Summary | Budget vs. actual, forecast, IPU utilization | Table + chart |
| Value Delivered | Business outcomes achieved this period | Bullet points + metrics |
| Risk Landscape | Top 5 risks with probability and impact | Risk heat map |
| Issues Summary | Open P1/P2 issues and resolution status | Table |
| Team & Resource Update | Staffing changes, capacity outlook | Narrative |
| Decisions & Escalations | Items requiring steering committee action | Numbered list |
| Next Month Preview | Key objectives and expected outcomes | Bullet points |

BEST PRACTICE

Keep the monthly executive report to 3-5 pages maximum. Executives scan for RAG status, risks, and decisions. Detailed analysis belongs in an appendix or linked reference.

# 4. Phase Completion Report

A phase completion report documents the outcomes of each major program phase (Discovery, Design, Build, Test, Deploy) and provides the basis for phase gate approval.

## 4.1 Phase Completion Report Structure

| Section | Content |
| --- | --- |
| Phase Overview | Phase objectives, scope, and timeline (planned vs. actual) |
| Deliverables Checklist | All planned deliverables with completion status |
| Quality Summary | Test results, defect summary, code review status |
| Metrics Summary | Key KPIs for the phase vs. targets |
| Risks Carried Forward | Unresolved risks to be managed in the next phase |
| Issues Closed / Open | Issue resolution summary and outstanding items |
| Lessons Learned | Top 5 lessons with actionable recommendations |
| Phase Gate Decision | Go / No-Go / Conditional Go recommendation |
| Next Phase Plan | Objectives, scope, resource plan for the upcoming phase |

## 4.2 Phase Gate Approval Criteria

All critical deliverables completed and accepted

No open P1 or unmitigated P2 issues

Budget variance within acceptable threshold (+/- 10%)

Stakeholder sign-off obtained from all required approvers

Next phase plan reviewed and resourced

# 5. Sprint Review Template

Sprint reviews showcase delivered work to stakeholders and gather feedback. The review template ensures consistent coverage and productive discussions.

## 5.1 Sprint Review Agenda

| Segment | Duration | Content | Presenter |
| --- | --- | --- | --- |
| Sprint Goals Recap | 5 min | What we committed to deliver | Scrum Master |
| Demo of Completed Work | 20 min | Live demonstration of delivered features | Developers |
| Metrics Review | 5 min | Velocity, burndown, quality metrics | Scrum Master |
| Stakeholder Feedback | 10 min | Questions, concerns, suggestions | All attendees |
| Next Sprint Preview | 5 min | Planned stories and goals | Product Owner |
| Action Items | 5 min | Capture follow-ups | Scrum Master |

## 5.2 Sprint Metrics Summary

| Metric | This Sprint | Previous Sprint | Trend |
| --- | --- | --- | --- |
| Planned Story Points | [X] | [Y] | [Up/Down/Flat] |
| Completed Story Points | [X] | [Y] | [Up/Down/Flat] |
| Velocity | [X] | [Y] | [Up/Down/Flat] |
| Defects Found | [X] | [Y] | [Up/Down/Flat] |
| Defects Fixed | [X] | [Y] | [Up/Down/Flat] |
| Carry-over Stories | [X] | [Y] | [Up/Down/Flat] |

WARNING

Sprint reviews are NOT status meetings. Focus on demonstrating working software and gathering feedback. Status discussions belong in the weekly status report.

# 6. Metrics Dashboard Template

The metrics dashboard provides a visual summary of program KPIs. Design the dashboard for at-a-glance comprehension with drill-down capability for investigation.

## 6.1 Dashboard Layout

| Section | Visualizations | Data Source |
| --- | --- | --- |
| Program Health | RAG indicators for schedule, budget, quality, scope | Project plan + financials |
| Delivery Velocity | Sprint burn-down chart, velocity trend line | Jira / ADO |
| Quality Metrics | Defect density chart, test pass rate gauge | Test management tool |
| IPU Consumption | IPU burn-rate chart, utilization by service | IICS monitoring API |
| Risk Heat Map | Probability vs. impact scatter plot | Risk register |
| Issue Aging | Open issues by age bucket (bar chart) | Issue tracker |

## 6.2 Dashboard Refresh Cadence

Real-time: IPU consumption, pipeline execution status

Daily: Defect counts, test results, sprint burndown

Weekly: Velocity trends, risk heat map, issue aging

Monthly: Budget variance, value realization metrics

# 7. Burn-Down / Burn-Up Charts

Burn-down and burn-up charts are essential agile reporting tools that visualize progress toward sprint and release goals.

## 7.1 Burn-Down Chart

A burn-down chart shows the remaining work (story points or tasks) over time. The ideal trend line slopes downward from the total planned work to zero by sprint end.

Y-axis: Remaining story points / tasks

X-axis: Sprint days

Ideal line: Straight diagonal from total to zero

Actual line: Daily plot of remaining work

## 7.2 Burn-Up Chart

A burn-up chart shows cumulative work completed against the total scope. It reveals scope changes that burn-down charts can hide.

Y-axis: Story points

X-axis: Sprint days or iterations

Scope line: Total scope (may increase over time)

Completed line: Cumulative completed work (should trend upward)

## 7.3 Interpreting Chart Patterns

| Pattern | Interpretation | Action |
| --- | --- | --- |
| Actual tracks ideal line | Team is on pace | Continue current approach |
| Actual above ideal (burn-down) | Behind schedule | Review blockers, reduce scope, add capacity |
| Actual below ideal (burn-down) | Ahead of schedule | Verify quality not sacrificed; pull next stories |
| Scope line increasing (burn-up) | Scope creep occurring | Invoke change control process |
| Flat actual line | Team blocked or no progress | Immediate investigation required |

# 8. Automated Reporting with IICS APIs

Informatica IICS provides REST APIs that enable automated collection of operational metrics. Automating data collection reduces manual effort and improves reporting accuracy.

## 8.1 Key IICS APIs for Reporting

| API Endpoint | Data Retrieved | Use Case |
| --- | --- | --- |
| Activity Log API | Job execution history, status, duration | Pipeline success/failure rates |
| Audit Log API | User actions, configuration changes | Change tracking, compliance |
| Metering API | IPU consumption by service and org | IPU utilization dashboards |
| Monitor API | Real-time job status and health | Operational dashboards |
| Object API | Asset inventory (mappings, connections) | Asset count and growth metrics |

## 8.2 Automation Architecture

A typical automated reporting pipeline follows this pattern:

Scheduler triggers data collection (e.g., daily at 6 AM).

Python or PowerShell script calls IICS REST APIs with OAuth2 authentication.

API responses are parsed and loaded into a reporting database or data warehouse.

Dashboard tool (Power BI, Tableau) refreshes visualizations from the reporting layer.

Automated email with dashboard snapshot sent to stakeholders per cadence.

## 8.3 Sample API Call

# Authenticate to IICS

POST https://dm-us.informaticacloud.com/saas/public/core/v3/login

Body: { "username": "<user>", "password": "<pass>" }

# Get Activity Log (last 24 hours)

GET https://na1.dm-us.informaticacloud.com/saas/api/v2/activity/activityLog

Headers: { "icSessionId": "<session_id>" }

Params: { "rowLimit": 200, "startedTimeAfter": "<ISO-timestamp>" }

AI/AGENTIC

Consider using CLAIRE AI recommendations from IICS monitoring to enrich automated reports with AI-driven insights on pipeline optimization and anomaly detection.

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| GOV_Program_Metrics_KPIs.docx | Governance Library |
| GOV_Stakeholder_Communication_Plan.docx | Governance Library |
| GOV_Issue_Escalation_Procedures.docx | Governance Library |
| GOV_Scope_Change_Control_Process.docx | Governance Library |
| TA_IDMC_API_Integration_Guide.docx | Technical Architecture |