# INFA Inventory Complexity Analysis

Mastech Digital — Informatica Platform Assets

Systematic inventory extraction and complexity scoring methodology for PowerCenter to IICS migration.

| Document | INFA Inventory Complexity Analysis |
| --- | --- |
| Category | Migration - Assessment |
| Document ID | #41 |
| Version | 1.0 |
| Date | February 2026 |
| Author | Mastech Digital — Informatica Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Informatica IDMC (IICS) – Early 2026 |
| Next Review | August 2026 |

# Executive Summary

Before any migration can be planned, the existing PowerCenter repository must be fully inventoried and each object scored for migration complexity. This document provides a rigorous methodology for extracting the complete PC inventory, categorizing objects by type, and applying a point-based complexity scoring system that drives wave prioritization.

The complexity scoring model evaluates transformation types, PC-specific features, error handling patterns, parameter file usage, database-specific SQL, and stored procedure dependencies. Objects are classified into four tiers: Low (1-3 points), Medium (4-6), High (7-10), and Very High (11+). Industry experience shows a typical distribution of 40% Low, 30% Medium, 20% High, and 10% Very High.

This analysis directly feeds into wave planning, resource estimation, and migration factory throughput calculations, enabling data-driven project planning.

# Table of Contents

1.0  PC Inventory Extraction Methods

2.0  Object Categorization Framework

3.0  Complexity Scoring Methodology

4.0  Complexity Tiers & Classification

5.0  Wave Prioritization Strategy

6.0  Migration Factory Throughput Estimation

7.0  Automated Inventory Extraction Scripts

8.0  Complexity Distribution Analysis

9.0  Visualization & Dashboard Recommendations

10.0  Appendix: Scoring Reference Tables

# Prerequisites & Applicability

pmrep CLI access to all PowerCenter repositories

Read access to PowerCenter repository database tables

Python 3.8+ for running inventory extraction scripts

Access to PowerCenter Designer for visual inspection

Folder-level permissions for all production folders

# 1. PC Inventory Extraction Methods

Two primary methods exist for extracting the PowerCenter inventory: the pmrep command-line interface and direct repository database queries. Both should be used for cross-validation.

## 1.1 pmrep Command-Line Extraction

The pmrep utility provides the most reliable method for inventory extraction.

#!/bin/bash

# ---- PowerCenter Inventory Extraction Script ----

REPO=PROD_REPO

DOMAIN=INFA_DOMAIN

USER=admin

PASS=<encrypted>

# Connect

pmrep connect -r $REPO -d $DOMAIN -n $USER -x $PASS

# Extract all object types

for OBJ_TYPE in mapping session workflow worklet mapplet; do

echo "=== Extracting $OBJ_TYPE ==="

pmrep listobjects -o $OBJ_TYPE -t > inventory_${OBJ_TYPE}.csv

done

# Extract folder list

pmrep listobjects -o folder > inventory_folders.csv

# Extract sources and targets

pmrep listobjects -o source > inventory_sources.csv

pmrep listobjects -o target > inventory_targets.csv

# Object dependencies for each mapping

while IFS=, read -r folder mapping; do

pmrep listobjectdependencies -o mapping -n "$mapping" -f "$folder" -p both \

>> dependencies.csv

done < inventory_mapping.csv

pmrep disconnect

## 1.2 Repository Database Queries

Direct queries against the PowerCenter repository database provide additional metadata.

-- Count all objects by type

SELECT SUBJECT_AREA AS folder,

OBJECT_TYPE,

COUNT(*) AS object_count

FROM   REP_ALL_OBJECTS

GROUP BY SUBJECT_AREA, OBJECT_TYPE

ORDER BY SUBJECT_AREA, OBJECT_TYPE;

-- List all mappings with transformation counts

SELECT m.SUBJECT_AREA AS folder,

m.MAPPING_NAME,

COUNT(w.WIDGET_ID) AS transformation_count

FROM   REP_ALL_MAPPINGS m

JOIN   REP_WIDGET_INST w ON m.MAPPING_ID = w.MAPPING_ID

GROUP BY m.SUBJECT_AREA, m.MAPPING_NAME

ORDER BY transformation_count DESC;

INFO

Always cross-validate pmrep output against repository database queries. Discrepancies may indicate orphaned objects or repository corruption.

# 2. Object Categorization Framework

All PowerCenter objects must be categorized by type for migration planning.

| Object Type | Description | Migration Approach | Typical Count % |
| --- | --- | --- | --- |
| Mappings | Core ETL logic: source-to-target transformations | Convert via Migration Wizard or manual | 35% |
| Sessions | Execution configuration for mappings | Recreated as mapping tasks in IICS | 25% |
| Workflows | Orchestration of sessions and commands | Convert to Taskflows in IICS | 15% |
| Worklets | Reusable workflow sub-components | Convert to sub-taskflows | 5% |
| Mapplets | Reusable mapping sub-components | Convert to shared mappings/mapplets | 5% |
| Transformations (reusable) | Shared transformation objects | Convert or recreate in IICS | 5% |
| Sources/Targets | Source and target definitions | Replace with IICS connections | 10% |

## 2.1 Object Dependency Mapping

Understanding dependencies is critical for wave planning. Objects with many dependencies must be migrated together to avoid breaking integration chains.

Mapping -> Source definitions, Target definitions, Reusable transformations, Mapplets

Session -> Mapping, Connection objects, Parameter files

Workflow -> Sessions, Worklets, Command tasks, Timer tasks, Decision tasks

Worklet -> Sessions, nested Worklets

WARNING

Circular dependencies between folders (Folder A references Folder B and vice versa) must be resolved before migration. These create wave sequencing conflicts.

# 3. Complexity Scoring Methodology

Each mapping is scored using a point-based system that evaluates six dimensions of complexity. Points are additive across dimensions.

## 3.1 Transformation Types Scoring

| Transformation Type | Points | Rationale |
| --- | --- | --- |
| Source Qualifier (basic) | 0 | Direct IICS equivalent |
| Expression | 0 | Direct equivalent (syntax minor differences) |
| Filter | 0 | Direct equivalent |
| Aggregator | 1 | Minor config differences |
| Joiner | 1 | Config differences (join type, condition) |
| Lookup (connected, simple) | 1 | Direct equivalent |
| Lookup (unconnected) | 2 | Requires redesign in IICS |
| Router | 1 | Direct equivalent |
| Union | 1 | Direct equivalent |
| Sorter | 1 | Direct equivalent |
| Rank | 1 | Direct equivalent |
| Normalizer (relational) | 2 | Different implementation in IICS |
| Normalizer (COBOL/VSAM) | 4 | Major redesign needed |
| XML Source/Target/Parser | 3 | Hierarchical processing differs significantly |
| Custom Transformation (Java) | 4 | Must rewrite as Java SDK or custom function |
| Custom Transformation (C) | 5 | No IICS equivalent; full rewrite |
| Stored Procedure | 3 | Must externalize or rewrite |
| HTTP Transformation | 2 | Map to REST V2 connector |
| SQL Transformation | 2 | IICS SQL transformation syntax differs |
| Transaction Control | 2 | Different paradigm in IICS |

## 3.2 PC-Specific Features Scoring

| Feature | Points | Rationale |
| --- | --- | --- |
| Pushdown Optimization | 1 | IICS ELT mode different configuration |
| Session Partitioning | 2 | Auto-partitioning in IICS, manual needs review |
| Incremental Aggregation | 2 | Not directly supported; must redesign |
| Late-arriving data handling | 2 | Different approach in IICS |
| Workflow recovery | 1 | Taskflow restart/recovery differs |
| Pre/Post session commands | 1 | Mapping task pre/post commands |
| Session level override (SQL) | 2 | Must embed in mapping or externalize |

## 3.3 Error Handling Complexity

| Pattern | Points | Notes |
| --- | --- | --- |
| Basic error logging (default) | 0 | Standard in IICS |
| Error rows redirected to file/table | 1 | Supported in IICS with config |
| Custom error handling with Decision tasks | 2 | Redesign in Taskflow |
| Row-level error trapping with Expression logic | 2 | Review expression syntax |
| Workflow-level abort/restart logic | 3 | Taskflow error paths |

## 3.4 Parameter File Usage

| Pattern | Points | Notes |
| --- | --- | --- |
| No parameters | 0 | No action needed |
| Simple mapping parameters | 1 | Map to IICS input/output parameters |
| Session-level parameter file (.par) | 2 | Convert to IICS parameter files or connection params |
| Workflow variable-based parameterization | 2 | Redesign using Taskflow variables |
| Dynamic parameter file paths | 3 | Complex; may need custom solution |

## 3.5 Database-Specific SQL

| Pattern | Points | Notes |
| --- | --- | --- |
| ANSI SQL only | 0 | Portable across databases |
| Minor DB-specific functions (NVL, ISNULL) | 1 | Expression rewrite |
| Complex DB-specific SQL (CONNECT BY, CTE) | 2 | Major rewrite of SQL overrides |
| Hints, optimizer directives | 1 | Remove or externalize |
| Stored procedure calls in SQL override | 3 | Must externalize |

## 3.6 Stored Procedures / External Procedures

| Pattern | Points | Notes |
| --- | --- | --- |
| No external procedures | 0 | No action |
| Simple stored procedure (data lookup) | 2 | Externalize to pre/post SQL or Lookup |
| Complex stored procedure (business logic) | 4 | Rewrite logic in IICS expressions or external call |
| External procedure (C/Java library) | 5 | Full rewrite required |

BEST PRACTICE

Automate complexity scoring using scripts that parse pmrep output. Manual scoring is error-prone and does not scale for repositories with 500+ mappings.

# 4. Complexity Tiers & Classification

Total complexity points determine the tier classification.

| Tier | Point Range | Conversion Approach | Effort per Mapping | Risk Level |
| --- | --- | --- | --- | --- |
| Low | 1-3 pts | Migration Wizard + minor manual adjustments | 2-4 hours | Low |
| Medium | 4-6 pts | Migration Wizard + moderate manual rework | 4-8 hours | Medium |
| High | 7-10 pts | Significant manual rework, testing | 8-24 hours | High |
| Very High | 11+ pts | Full manual redesign and rewrite | 24-80 hours | Very High |

CRITICAL

Very High complexity mappings (11+ pts) often take 5-10x longer than Low complexity. Budget accordingly and assign senior developers to these objects.

# 5. Wave Prioritization Strategy

Wave-based migration reduces risk by starting with the simplest objects, validating the approach, and progressively tackling more complex items.

## 5.1 Recommended Wave Structure

| Wave | Scope | Complexity Tier | Duration | Objective |
| --- | --- | --- | --- | --- |
| Wave 0 (POC) | 5-10 mappings | Low | 2 weeks | Validate tooling and approach |
| Wave 1 (Pilot) | 30-50 mappings | Low | 4-6 weeks | Build team confidence, refine estimates |
| Wave 2 | 80-120 mappings | Low + Medium | 6-8 weeks | Scale factory model |
| Wave 3 | 60-80 mappings | Medium + High | 8-10 weeks | Handle complex patterns |
| Wave 4 | 20-40 mappings | High + Very High | 8-12 weeks | Specialist-driven rewrites |

## 5.2 Wave Sequencing Rules

Never mix Very High complexity with Low in the same wave

Respect dependency chains: parent objects migrate before children

Group by business domain to enable focused UAT

SOX/HIPAA critical flows get their own dedicated wave with enhanced controls

INFO

Wave 0 (POC) is non-negotiable. Skip it at your peril. Every assumption about migration tooling must be validated before committing to factory execution.

# 6. Migration Factory Throughput Estimation

Migration factory throughput determines project duration and staffing requirements.

| Metric | Low Complexity | Medium | High | Very High |
| --- | --- | --- | --- | --- |
| Mappings/developer/sprint (2wk) | 15-20 | 8-12 | 3-5 | 1-2 |
| Testing effort per mapping | 1-2 hrs | 2-4 hrs | 4-8 hrs | 8-16 hrs |
| Defect rate (first pass) | 5-10% | 15-25% | 30-40% | 50-70% |
| Rework effort per defect | 0.5-1 hr | 1-2 hrs | 2-4 hrs | 4-8 hrs |

## 6.1 Throughput Calculation Example

For a repository with 400 mappings (40% Low, 30% Med, 20% High, 10% Very High):

# Throughput calculation

low_mappings = 400 * 0.40     # 160 mappings

med_mappings = 400 * 0.30     # 120 mappings

high_mappings = 400 * 0.20    #  80 mappings

vhigh_mappings = 400 * 0.10   #  40 mappings

# Developer-sprints needed (2-week sprints, avg throughput)

low_sprints = 160 / 17        #  9.4 sprints

med_sprints = 120 / 10        # 12.0 sprints

high_sprints = 80 / 4         # 20.0 sprints

vhigh_sprints = 40 / 1.5      # 26.7 sprints

# With 6 developers, parallel execution:

total_sprints = (9.4 + 12.0 + 20.0 + 26.7) / 6  # ~11.3 sprints

# Duration: ~23 weeks (11.3 x 2) + overhead = ~26 weeks

# 7. Automated Inventory Extraction Scripts

Python scripts automate inventory extraction and complexity scoring for large repositories.

## 7.1 Python Inventory Extractor

import subprocess

import csv

from pathlib import Path

PMREP = 'pmrep'

REPO = 'PROD_REPO'

DOMAIN = 'INFA_DOMAIN'

USER = 'admin'

def connect():

subprocess.run([PMREP, 'connect', '-r', REPO, '-d', DOMAIN,

'-n', USER, '-x', 'encrypted_pwd'], check=True)

def list_objects(obj_type, folder=None):

cmd = [PMREP, 'listobjects', '-o', obj_type, '-t']

if folder:

cmd.extend(['-f', folder])

result = subprocess.run(cmd, capture_output=True, text=True)

lines = [l.strip() for l in result.stdout.splitlines() if l.strip()]

return lines

def extract_inventory(output_dir='./inventory'):

Path(output_dir).mkdir(exist_ok=True)

connect()

for obj_type in ['mapping', 'session', 'workflow', 'worklet',

'mapplet', 'source', 'target']:

objects = list_objects(obj_type)

with open(f'{output_dir}/{obj_type}_inventory.csv', 'w') as f:

writer = csv.writer(f)

writer.writerow(['folder', 'name'])

for obj in objects:

parts = obj.split(',')

if len(parts) >= 2:

writer.writerow(parts[:2])

print(f'Extracted {len(objects)} {obj_type}s')

if __name__ == '__main__':

extract_inventory()

## 7.2 Python Complexity Scorer

import csv

TRANSFORM_SCORES = {

'Aggregator': 1, 'Joiner': 1, 'Lookup': 1,

'Unconnected Lookup': 2, 'Normalizer': 2,

'XML Parser': 3, 'Custom Transformation': 4,

'Stored Procedure': 3, 'HTTP': 2,

'SQL Transformation': 2, 'Transaction Control': 2,

}

def score_mapping(transforms: list) -> int:

total = 0

for t in transforms:

total += TRANSFORM_SCORES.get(t, 0)

return total

def classify(score: int) -> str:

if score <= 3: return 'Low'

if score <= 6: return 'Medium'

if score <= 10: return 'High'

return 'Very High'

def process_inventory(inventory_csv, output_csv):

with open(inventory_csv) as f_in, open(output_csv, 'w') as f_out:

reader = csv.DictReader(f_in)

writer = csv.writer(f_out)

writer.writerow(['mapping', 'score', 'tier'])

for row in reader:

transforms = row.get('transforms', '').split(';')

score = score_mapping(transforms)

writer.writerow([row['mapping'], score, classify(score)])

AI/AGENTIC

AI-powered code analysis tools can automatically detect complexity patterns such as dynamic SQL generation, conditional transformation logic, and implicit data type conversions that manual scoring may miss.

# 8. Complexity Distribution Analysis

Based on industry experience across 50+ PowerCenter migration engagements, the typical complexity distribution follows a predictable pattern.

| Tier | Expected % | Typical Range | Migration Effort Share |
| --- | --- | --- | --- |
| Low (1-3) | 40% | 35-50% | 15% of total effort |
| Medium (4-6) | 30% | 25-35% | 25% of total effort |
| High (7-10) | 20% | 15-25% | 30% of total effort |
| Very High (11+) | 10% | 5-15% | 30% of total effort |

Note the inverse relationship: Very High complexity mappings represent only 10% of objects but consume 30% of total migration effort. This insight is critical for resource planning.

WARNING

If your distribution shows >15% Very High complexity, re-evaluate the migration timeline and consider a phased approach with interim PC-IICS coexistence.

## 8.1 Distribution Anomalies

Watch for these red flags in your distribution analysis:

>60% Low complexity: May indicate incomplete scoring or missing custom transforms

>20% Very High complexity: Repository has significant technical debt; consider refactoring before migration

<10% Low complexity: Unusual; verify scoring methodology is not over-counting

# 9. Visualization & Dashboard Recommendations

Effective visualization of inventory and complexity data enables stakeholder communication and decision-making.

## 9.1 Recommended Charts

| Chart Type | Data Shown | Audience | Tool |
| --- | --- | --- | --- |
| Pie Chart | Complexity tier distribution | Executives | Power BI / Tableau |
| Stacked Bar | Complexity by folder/domain | Technical Leads | Power BI / Tableau |
| Heatmap | Folder x Complexity tier density | Migration Leads | Python matplotlib |
| Burndown | Migration progress by wave | Program Manager | Jira / Azure DevOps |
| Scatter Plot | Transformation count vs effort estimate | Architects | Python seaborn |

## 9.2 Dashboard Components

Total object count by type (live refresh from inventory database)

Complexity distribution donut chart (updated as scoring progresses)

Wave assignment status (assigned vs unassigned objects)

Migration progress tracker (converted, tested, deployed per wave)

Defect density trend by complexity tier

BEST PRACTICE

Publish a migration dashboard on Power BI or Tableau that auto-refreshes daily. Transparency builds stakeholder confidence and surfaces risks early.

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| #40 INFA Migration Readiness Assessment | Migration_Library/Assessment/ |
| #42 INFA Migration Testing Strategy | Migration_Library/Testing/ |
| #43 INFA Data Reconciliation Framework | Migration_Library/Testing/ |
| #02 INFA Secure Agent Deep Dive | Core_Library/Infrastructure/ |