# INFA PC to IICS Migration Guide

Mastech Digital — Informatica Platform Assets

Comprehensive guide for migrating from PowerCenter to Informatica Intelligent Cloud Services (IICS).

| Document | INFA PC to IICS Migration Guide |
| --- | --- |
| Category | Migration - PC to IICS |
| Document ID | #36 |
| Version | 1.0 |
| Date | February 2026 |
| Author | Mastech Digital — Informatica Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Informatica IDMC (IICS) – Early 2026 |
| Next Review | August 2026 |

# Executive Summary

Migrating from Informatica PowerCenter (PC) to Informatica Intelligent Cloud Services (IICS) is a strategic initiative that modernizes data integration, reduces infrastructure overhead, and unlocks cloud-native capabilities such as elastic scaling, CLAIRE AI recommendations, and serverless execution. This guide defines the 7-Phase Migration Factory methodology, wave planning with complexity scoring, automated conversion accelerators, parallel run strategy, and cutover planning to ensure a controlled, risk-managed transition.

# Table of Contents

1.0  Migration Approach Options

2.0  7-Phase Migration Factory

3.0  Wave Planning & Complexity Scoring

4.0  Migration Accelerator Tool

5.0  Parallel Run & Cutover Strategy

6.0  CLAIRE AI Acceleration

7.0  Risk Management & Quality Gates

8.0  Timeline Estimates

9.0  Prerequisites & Applicability

10.0  Related Assets

# Prerequisites & Applicability

Informatica PowerCenter 10.2+ currently in production

IICS Org provisioned with CDI (Cloud Data Integration) license

Secure Agent installed and registered on target runtime environment

Network connectivity between Secure Agent, source/target databases, and IICS cloud

PowerCenter repository metadata export (XML or repository query access)

Migration Accelerator license (included with IICS Advanced package)

Dedicated migration team with PC and IICS skills

# 1. Migration Approach Options

Organizations must choose the right migration strategy for each workload. The three primary approaches are lift-and-shift, refactor, and retire.

| Approach | Description | When to Use | Effort |
| --- | --- | --- | --- |
| Lift-and-Shift | Automated 1:1 conversion of PC objects to IICS equivalents | Simple mappings, standard transformations, tight timelines | Low |
| Refactor | Redesign mappings to leverage IICS-native features (pushdown, serverless) | Complex workflows, performance-critical jobs, ELT candidates | Medium-High |
| Retire | Decommission obsolete or redundant mappings without migration | Unused workflows, duplicate logic, legacy feeds with no consumers | Minimal |
| Replatform | Move to a different IICS service (e.g., CDI-E, CDGC, CAI) | Stored procedures, real-time CDC, API-driven orchestration | Medium |

BEST PRACTICE

Start with lift-and-shift for 60-70% of simple mappings to build momentum, then refactor complex/high-value pipelines in later waves.

# 2. 7-Phase Migration Factory

The Migration Factory follows a repeatable 7-phase lifecycle per wave.

| Phase | Name | Key Activities | Exit Criteria |
| --- | --- | --- | --- |
| 1 | Assess | Inventory PC objects, classify complexity, identify dependencies | Complexity-scored inventory spreadsheet signed off |
| 2 | Prepare | Set up IICS Org, Secure Agent, connections, naming standards | Target environment validated with smoke test |
| 3 | Convert | Run Migration Accelerator or manual conversion; resolve errors | All objects converted with zero critical errors |
| 4 | Validate | Unit test each mapping; compare row counts and data checksums | 100% pass on validation checklist |
| 5 | Organize | Assign folders/projects, apply naming conventions, tag assets | Governance review approved |
| 6 | Productionize | Configure schedules, alerts, SLA monitors; run parallel | Parallel run shows <1% variance for 3 cycles |
| 7 | Optimize | Enable pushdown optimization, tune memory, refactor hot paths | Performance baseline meets or exceeds PC benchmarks |

INFO

Each phase has a formal quality gate. Do not proceed to the next phase until exit criteria are met and documented.

## 2.1 Phase Details - Assess

The Assess phase inventories every PowerCenter object (mappings, sessions, workflows, worklets, mapplets) and assigns a complexity score. Use repository queries or the Migration Accelerator's assessment report.

-- PC Repository Query: Object Inventory Count

SELECT SUBJECT_AREA AS folder,

OBJECT_TYPE,

COUNT(*) AS obj_count

FROM   OPB_OBJECT_TYPE ot

JOIN   OPB_SUBJECT      s ON ot.SUBJ_ID = s.SUBJ_ID

GROUP BY SUBJECT_AREA, OBJECT_TYPE

ORDER BY obj_count DESC;

# 3. Wave Planning & Complexity Scoring

Divide the migration into waves of 30-60 mappings each. Each mapping receives a complexity score that drives effort estimation and resource allocation.

| Complexity | Criteria | Effort (hrs) | Auto-Convert? |
| --- | --- | --- | --- |
| Low | <=5 transformations, standard sources/targets, no lookups | 2-4 | Yes |
| Medium | 6-15 transformations, 1-3 lookups, simple expressions | 4-8 | Partial |
| High | 16-30 transformations, complex SQL overrides, dynamic lookups | 8-20 | Manual review |
| Very High | Stored procedures, external procedures, Java transforms, custom code | 20-40 | Manual rewrite |

WARNING

Very High complexity objects may require replatforming to CAI or custom connectors. Plan these in dedicated waves with specialist resources.

## 3.1 Wave Planning Template

| Wave | Scope | Complexity Mix | Duration | Team Size |
| --- | --- | --- | --- | --- |
| Wave 1 (Pilot) | 10-15 Low mappings | 100% Low | 2 weeks | 2 devs |
| Wave 2 | 30 Low + 10 Medium | 75% L / 25% M | 3 weeks | 3 devs |
| Wave 3 | 20 Medium + 10 High | 50% M / 50% H | 4 weeks | 4 devs |
| Wave 4 | 15 High + 5 Very High | 75% H / 25% VH | 5 weeks | 5 devs |
| Wave 5 (Final) | Remaining + cleanup | Mixed | 3 weeks | 3 devs |

# 4. Migration Accelerator Tool

The Informatica Migration Accelerator automates conversion of PowerCenter objects to IICS CDI assets. It handles source/target definitions, expressions, lookups, joiners, and standard transformations.

## 4.1 Automated vs Manual Conversion

| Feature | Automated | Manual |
| --- | --- | --- |
| Simple expressions | Yes | N/A |
| Lookup transformations | Yes (static) | Dynamic lookups |
| Source Qualifier SQL override | Partial | Complex overrides |
| Session properties | Most settings | Custom Java/C code |
| Workflow scheduling | No | Recreate in IICS |
| Parameter files | Converted to in-cloud params | Complex tokenization |

AI/AGENTIC

CLAIRE AI in IICS can suggest mapping optimizations post-conversion, including pushdown candidates and expression simplification.

# Migration Accelerator CLI Example

infamigrate export \

--repository PC_PROD_REPO \

--domain INFA_DOM \

--folder Sales_ETL \

--output /export/sales_etl.xml

infamigrate convert \

--input /export/sales_etl.xml \

--target-org my-iics-org \

--output /converted/sales_etl_iics.zip

# 5. Parallel Run & Cutover Strategy

Parallel runs execute both PC and IICS pipelines simultaneously to validate data equivalence before cutover.

## 5.1 Parallel Run Steps

Run PC workflow on scheduled cycle (production data)

Run IICS mapping task on same data window

Compare row counts, checksums (MD5/SHA256), and key business metrics

Document variances and investigate any delta > 0.1%

Repeat for minimum 3 consecutive cycles with zero variance

Obtain sign-off from data steward and business owner

CRITICAL

Never cut over production without completing at least 3 clean parallel runs. Any data variance must be root-caused and resolved before proceeding.

## 5.2 Cutover Checklist

All parallel runs passed with zero data variance

IICS schedules configured and tested (dry run)

Alerting and monitoring configured (email, SNMP, or REST webhooks)

Rollback plan documented and tested

PC workflows disabled (not deleted) for rollback safety

Communication sent to downstream consumers

# 6. CLAIRE AI Acceleration

CLAIRE (Cloud-scale AI Real-time Engine) provides AI-driven recommendations throughout the migration lifecycle.

Mapping Recommendations: Suggests transformations based on source/target schema

Performance Tuning: Identifies pushdown optimization candidates

Anomaly Detection: Flags data quality issues in migrated pipelines

Auto-Documentation: Generates lineage and impact analysis

AI/AGENTIC

Enable CLAIRE recommendations in Org Admin > AI/ML Settings. CLAIRE learns from your organization's patterns over time.

# 7. Risk Management & Quality Gates

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Unsupported transformations | High | Medium | Identify in Assess phase; plan manual rewrite |
| Data variance post-migration | Critical | Low | Parallel runs with checksum validation |
| Performance regression | High | Medium | Baseline PC metrics; tune IICS pushdown/partitioning |
| Connection failures | Medium | Low | Test all connections before Convert phase |
| Schedule conflicts during cutover | Medium | Medium | Cutover during maintenance window; disable PC first |

# 8. Timeline Estimates

Typical migration timeline for a mid-size PowerCenter estate (200-500 mappings):

| Phase | Duration | Cumulative |
| --- | --- | --- |
| Assess | 2-3 weeks | Week 3 |
| Prepare | 1-2 weeks | Week 5 |
| Wave 1 (Pilot) | 2-3 weeks | Week 8 |
| Waves 2-4 (Bulk) | 8-12 weeks | Week 20 |
| Wave 5 (Cleanup) | 2-3 weeks | Week 23 |
| Parallel Runs | 3-4 weeks | Week 27 |
| Cutover + Optimize | 2-3 weeks | Week 30 |

INFO

Total elapsed time for 200-500 mappings: approximately 6-8 months. Larger estates (1000+) may require 12-18 months with multiple parallel tracks.

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| INFA Object Conversion Playbook (#37) | Migration_Library/PC_to_IICS/ |
| INFA CDI Mapping Development Guide | Development_Library/CDI/ |
| INFA Secure Agent Installation Guide | Platform_Library/Runtime/ |
| INFA Connection Configuration Playbook | Platform_Library/Connections/ |
| INFA Monitoring & Alerting Runbook | Operations_Library/Monitoring/ |