Reltio MDM Implementation Guide

IBM InfoSphere MDM to Reltio Cloud MDM Migration

Mastech Digital — Reltio MDM Platform Assets

End-to-end migration playbook for replacing IBM InfoSphere MDM with Reltio Cloud MDM

| Document | IBM InfoSphere MDM to Reltio Cloud MDM Migration |
| --- | --- |
| Category | Platform Migration |
| Document ID | MIG-IBM-001 |
| Version | 1.0 |
| Date | March 2026 |
| Author | Mastech Digital — Reltio Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Reltio Cloud MDM – 2026 |
| Next Review | September 2026 |

# Executive Summary

IBM InfoSphere MDM has been a market-leading MDM platform for two decades, but its on-premise architecture, high total cost of ownership, and complex maintenance model are driving enterprises to modern cloud-native alternatives. Reltio Cloud MDM delivers equivalent MDM capabilities with a SaaS deployment model, API-first architecture, and built-in AI/ML — at significantly lower TCO. This migration guide provides Mastech Digital's proven methodology for migrating from IBM InfoSphere MDM to Reltio, covering architectural mapping, data model conversion, match rule translation, integration re-platforming, and production cutover strategy.

# Table of Contents

1.0  Platform Comparison

2.0  Migration Methodology Overview

3.0  Data Model Migration

4.0  Match & Merge Rule Migration

5.0  Integration Re-platforming

6.0  Stewardship & Workflow Migration

7.0  Data Extraction & Transformation

8.0  Cutover Strategy

9.0  Post-Migration Validation

10.0  Common Migration Challenges

# 1. Platform Comparison

## 1.1 IBM InfoSphere MDM vs. Reltio Cloud MDM

| Dimension | IBM InfoSphere MDM | Reltio Cloud MDM |
| --- | --- | --- |
| Deployment | On-premise / private cloud | SaaS — fully managed on GCP |
| Architecture | J2EE application server, DB2/Oracle | Cloud-native microservices, graph DB |
| MDM Style | Registry, Hub, Coexistence modes | Hub & Coexistence (configurable) |
| Match Engine | Probabilistic matching service (PMS) | ML + rule-based hybrid match engine |
| Data Model | XML-based physical data model (PDM) | JSON entity model with schema registry |
| Integration | MQ/JMS, WebSphere, SOAP services | REST API, Kafka, pre-built connectors |
| Stewardship UI | IBM MDM Business Console (complex) | Reltio UI (modern, configurable) |
| Scalability | Vertical scaling — hardware-bound | Elastic cloud scaling, multi-tenant |
| Upgrade | Major version upgrades every 2-3 years | Continuous updates, zero downtime |
| TCO (5-year typical) | $3-8M (infra + license + ops) | $0.8-2.5M (SaaS, reduced ops overhead) |

## 1.2 IBM MDM Deployment Mode Mapping

| IBM MDM Mode | Description | Reltio Equivalent |
| --- | --- | --- |
| Registry Style | Cross-reference index; source systems authoritative | Registry MDM (Reltio XREF mode) |
| Consolidation Hub | Reltio as system of record with best-version golden record | Hub MDM (full Reltio survivorship) |
| Coexistence Style | Shared ownership: IBM + source systems co-manage attributes | Reltio coexistence with source priority per attribute |
| Transaction Hub | MDM participates in real-time transactions | Reltio real-time REST API mode |

# 2. Migration Methodology Overview

## 2.1 Mastech 5-Phase IBM-to-Reltio Migration

| Phase | Name | Duration | Key Activities |
| --- | --- | --- | --- |
| 1 | Assessment & Planning | 4-6 weeks | IBM MDM inventory, data profiling, gap analysis, migration architecture design |
| 2 | Reltio Design | 6-8 weeks | Entity model design, match rule conversion, survivorship design, integration architecture |
| 3 | Build & Configure | 8-12 weeks | Reltio tenant configuration, integration build, data transformation scripts |
| 4 | Migration & Testing | 6-8 weeks | Data extraction, transformation, bulk load, SIT/UAT, match quality validation |
| 5 | Cutover & Stabilize | 4-6 weeks | Parallel run, production cutover, hypercare, IBM MDM decommission plan |

INFO

Run IBM InfoSphere MDM and Reltio in parallel for a minimum of 4 weeks before final cutover. Parallel run is non-negotiable — it is the primary risk mitigation for match quality and integration fidelity.

# 3. Data Model Migration

## 3.1 IBM MDM Physical Data Model → Reltio Entity Model

IBM InfoSphere MDM stores master data in a physical database schema (PDM) with party, product, and account tables. Each IBM MDM Party entity type maps to a Reltio entity type. The translation requires schema analysis, attribute mapping, and relationship re-modeling.

| IBM MDM Construct | Reltio Equivalent | Migration Action |
| --- | --- | --- |
| Party (PARTY table) | com.example.Individual or Organization entity type | Create entity type with equivalent attributes |
| Party type discriminator | Entity type URI | Map each IBM party type to a distinct Reltio entity type |
| Party attributes (columns) | Reltio attributes (JSON) | Map column → attribute; apply naming conventions |
| Address subtype table | addresses[] attribute group | Flatten into attribute group with type discriminator |
| Phone subtype table | phones[] attribute group | Flatten into attribute group |
| Identifier table (PARTY_IDENTIFIER) | identifiers[] attribute group + cross-references | Identifiers become XREFs if source-system IDs |
| Relationship table (PARTY_RELATIONSHIP) | Reltio relationship entities | Recreate as named relationship types |
| Hierarchy table (PARTY_HIERARCHY) | Reltio hierarchy entity type | Recreate with parent-child relationships |
| Source system table (XREF) | crossReferences[] on entity | Direct mapping — IBM XREFs become Reltio XREFs |
| Merge history table | Reltio audit log + potentialDuplicates | Historical merges re-run through Reltio match |

## 3.2 Attribute Data Type Mapping

| IBM MDM Type (DB2/Oracle) | Reltio Attribute Type | Notes |
| --- | --- | --- |
| VARCHAR(n) | string, maxLength: n | Direct mapping |
| CHAR(n) | string, maxLength: n | Trim trailing spaces during ETL |
| TIMESTAMP | datetime | Convert to ISO 8601 format |
| DATE | date | Convert to YYYY-MM-DD |
| NUMBER / DECIMAL | number | Preserve precision in schema |
| CLOB / NCLOB | string | Truncate at Reltio maxLength or store as reference |
| CHAR(1) flag columns | boolean | Map Y/N or 1/0 to true/false |
| Lookup code columns | enum or string | Create Reltio enum if controlled vocabulary; else string |

# 4. Match & Merge Rule Migration

## 4.1 IBM Probabilistic Matching Service (PMS) → Reltio Match Engine

IBM InfoSphere MDM's Probabilistic Matching Service (PMS) uses a configuration-driven algorithm with comparison functions, weights, and thresholds. The Reltio match engine uses a similar probabilistic model but with a JSON-based configuration format.

| IBM PMS Concept | Reltio Equivalent | Migration Notes |
| --- | --- | --- |
| Match specification (XML) | Match rule set (JSON) | Rewrite in Reltio format; preserve weights |
| Standardization rules | Normalization functions on match attributes | Apply same standardization in Reltio rule config |
| Comparison function (e.g., ML_LASTNAME) | matchType: JARO_WINKLER or LEVENSHTEIN | Map IBM comparison functions to Reltio algorithms |
| Weight per attribute | weight per condition in rule | Normalize IBM weights to Reltio 0.0-1.0 scale |
| Duplicate threshold | reviewThreshold in rule set | Convert IBM threshold scale to Reltio 0-1 scale |
| Merge threshold | mergeThreshold in rule set | Calibrate via test run on production data sample |
| Blocking keys | Blocking conditions in rule config | Re-map IBM bucket keys to Reltio blocking attributes |
| Deterministic match rules | DETERMINISTIC rule type | Direct equivalent — configure in Reltio JSON |

## 4.2 PMS Weight Conversion Formula

# IBM PMS uses weights 0-100; Reltio uses 0.0-1.0

# Conversion:

reltio_weight = ibm_weight / 100.0

# IBM PMS threshold is typically 60-90; Reltio uses 0.6-0.9

# Conversion:

reltio_threshold = ibm_threshold / 100.0

# Example IBM PMS rule:

# <attribute name="LAST_NAME" weight="35" comparison="ML_LASTNAME" threshold="0.8"/>

# <attribute name="FIRST_NAME" weight="20" comparison="ML_FIRSTNAME" threshold="0.75"/>

# <attribute name="BIRTH_DATE" weight="25" comparison="EXACT" threshold="1.0"/>

# merge_threshold = 85, review_threshold = 65

# Becomes Reltio:

# {

#   "conditions": [

#     {"attribute": "lastName",  "matchType": "JARO_WINKLER", "weight": 0.35, "minThreshold": 0.80},

#     {"attribute": "firstName", "matchType": "JARO_WINKLER", "weight": 0.20, "minThreshold": 0.75},

#     {"attribute": "birthDate", "matchType": "EXACT",        "weight": 0.25}

#   ],

#   "mergeThreshold": 0.85,

#   "reviewThreshold": 0.65

# }

BEST PRACTICE

Do not blindly port IBM PMS thresholds to Reltio. Always re-calibrate on a 1,000-pair sample from production data. IBM PMS and Reltio scoring algorithms differ and the same weights/thresholds will produce different precision/recall results.

# 5. Integration Re-platforming

## 5.1 IBM MDM Integration Architecture → Reltio

| IBM MDM Integration | Reltio Equivalent | Re-platform Effort |
| --- | --- | --- |
| IBM SIF (Service Interface Framework) SOAP API | Reltio REST API (JSON) | Medium — rewrite API clients |
| IBM MQ / JMS messaging | Reltio Streams (Kafka-compatible) | Medium — migrate MQ consumers to Kafka |
| IBM MDM Publish/Subscribe | Reltio Streams subscriptions | Low — similar pattern, different protocol |
| IBM WebSphere Integration | Reltio REST API / Kafka | High — rebuild integration layer |
| IBM DataStage ETL | Python/dbt ETL to Reltio Bulk API | Medium — rebuild transformation scripts |
| IBM MDM Business Console | Reltio UI + custom stewardship UI | Low — configure Reltio; train stewards |
| IBM MDM batch jobs (DB2 SQL) | Reltio Bulk API + Airflow orchestration | Medium — rebuild batch layer |

## 5.2 SIF → Reltio REST API Migration Pattern

# IBM SIF SOAP call (legacy):

# <soapenv:Envelope>

#   <soapenv:Body>

#     <put:putSourceContribution>

#       <put:party>

#         <party:SourceKey>SF-12345</party:SourceKey>

#         <party:FirstName>Jane</party:FirstName>

#         <party:LastName>Doe</party:LastName>

#       </put:party>

#     </put:putSourceContribution>

#   </soapenv:Body>

# </soapenv:Envelope>

# Equivalent Reltio REST API call:

PUT https://prod.reltio.com/reltio/api/{tenant}/entities

?crossReferences=com.example.SOURCE:SF-12345

Content-Type: application/json

Authorization: Bearer {token}

{

"type": "com.example.Individual",

"crossReferences": [{"type": "com.example.SOURCE", "value": "SF-12345"}],

"attributes": {

"firstName": [{"value": "Jane"}],

"lastName":  [{"value": "Doe"}]

}

}

# 6. Stewardship & Workflow Migration

## 6.1 IBM MDM Business Console → Reltio UI

| IBM Business Console Feature | Reltio Equivalent | Configuration Required |
| --- | --- | --- |
| Suspect duplicate review queue | Reltio Potential Duplicates queue | Match rule review threshold |
| Task management / work queues | Reltio Workflow task queue | Stewardship workflow configuration |
| Data editing / correction | Reltio entity edit UI | Role-based edit permissions |
| Merge / Unmerge UI | Reltio Merge/Unmerge interface | No extra config required |
| Audit trail | Reltio Audit log | Enabled by default |
| DQ dashboards | Reltio Analytics + custom dashboards | DQ rules configuration |
| Search / query interface | Reltio entity search + filter API | Search index configuration |

## 6.2 Steward Retraining Plan

Duration: 2-day structured training + 1-week supervised operation period

Content: Reltio UI navigation, exception resolution, merge/unmerge, DQ dashboard

Comparison: Focus on IBM → Reltio workflow equivalents, not just new features

Super-user program: Identify 2-3 power users per domain for peer support

Reference guide: Quick-reference card mapping IBM Business Console screens to Reltio UI

# 7. Data Extraction & Transformation

## 7.1 IBM MDM Data Extraction Strategy

| Data Layer | Extraction Method | Target Format |
| --- | --- | --- |
| Party master data (PDM tables) | DB2/Oracle SQL extract to CSV/Parquet | Reltio JSON entities |
| Cross-reference data (XREF tables) | SQL extract → map to Reltio crossReferences[] | Reltio XREF format |
| Relationship data | SQL extract from relationship tables | Reltio relationship API format |
| Hierarchy data | SQL extract from hierarchy tables | Reltio hierarchy entity format |
| Source system contributions | Extract per source, preserve source XREFs | One file per source system |
| Merge history | Optional — use for match calibration only | Not directly loaded to Reltio |

## 7.2 Transformation Pipeline

# IBM MDM DB2 extract → Reltio JSON transformation (Python)

import pandas as pd, json

# Read IBM MDM party extract

df = pd.read_csv('ibm_mdm_party_extract.csv', dtype=str)

def transform_row(row):

entity = {

"type": "com.example.Individual",

"crossReferences": [

{"type": "com.example.IBM_MDM_PARTY", "value": row['PARTY_ID']}

],

"attributes": {

"firstName":  [{"value": row['FIRST_NAME'].strip()}] if pd.notna(row['FIRST_NAME']) else [],

"lastName":   [{"value": row['LAST_NAME'].strip()}]  if pd.notna(row['LAST_NAME']) else [],

"birthDate":  [{"value": row['BIRTH_DT'].strftime('%Y-%m-%d')}] if pd.notna(row['BIRTH_DT']) else [],

}

}

# Add source system XREFs from IBM XREF table

for src in get_xrefs(row['PARTY_ID']):

entity["crossReferences"].append({

"type": f"com.example.{src['source_type']}",

"value": src['source_key']

})

return entity

# Write one entity per line (JSON Lines format for Reltio Bulk API)

with open('reltio_entities.jsonl', 'w') as f:

for _, row in df.iterrows():

f.write(json.dumps(transform_row(row)) + '\n')

# 8. Cutover Strategy

## 8.1 Parallel Run Architecture

PARALLEL RUN ARCHITECTURE (4-6 weeks):

Source Systems

│

├────▶  IBM InfoSphere MDM (READ ONLY after cutover-minus-2-weeks)

│            │

│            ▼ (outbound sync paused)

│       Downstream Systems

│

└────▶  Reltio Cloud MDM (ACTIVE — receives all new/changed data)

│

▼

Downstream Systems (verify parity with IBM output)

COMPARISON ENGINE: Daily reconciliation comparing:

- Entity count by source system

- Golden record attribute values (sample 500/day)

- Match decisions (same pairs merged in both platforms?)

- Exception volumes

## 8.2 Cutover Go/No-Go Criteria

| Criterion | Threshold | Blocking? |
| --- | --- | --- |
| Reltio entity count vs. IBM entity count | Within ±2% | Yes |
| Golden record attribute match rate (sample) | > 97% agreement | Yes |
| Reltio match precision | > 94% | Yes |
| All source system integrations active on Reltio | 100% | Yes |
| Steward team trained and qualified | 100% of stewards | Yes |
| Open P1 defects | 0 | Yes |
| IBM MDM in read-only mode confirmed | Operations team sign-off | Yes |

# 9. Post-Migration Validation

## 9.1 Validation Checklist

| Validation Area | Method | Success Criteria |
| --- | --- | --- |
| Entity count parity | API count vs. IBM table count | < 2% variance |
| Golden record accuracy | Sample 200 records, compare attributes | > 98% accurate |
| Match quality | Review 100 merged pairs + 100 non-matches | > 95% correct decisions |
| XREF completeness | Count XREFs per source system | No source system XREFs missing |
| Relationship completeness | Count relationships by type | < 1% variance vs. IBM |
| Downstream system data parity | Run downstream system reports in both systems | Key reports match |
| DQ score baseline | Run DQ rules on production data | Establish baseline, monitor trend |

# 10. Common Migration Challenges

| Challenge | Root Cause | Mitigation |
| --- | --- | --- |
| IBM PDM complexity | IBM's physical data model has 200+ tables with complex joins | Engage IBM MDM expert during schema analysis phase |
| PMS weight miscalibration | Direct weight conversion produces wrong precision/recall | Always recalibrate on production sample after conversion |
| SOAP → REST client rewrites | Large number of SOAP API consumers across enterprise | Inventory all consumers; prioritize by criticality; staged migration |
| IBM merge history gaps | IBM merge history not fully reconstructable in Reltio | Accept as known limitation; run fresh match in Reltio |
| Business Console user resistance | Stewards trained on IBM UI for years | Invest heavily in super-user program and reference guides |
| Performance gap during initial load | IBM DB2 extract is slow for large datasets | Extract in parallel by partition; use IBM export utilities |
| IBM-specific customizations | Custom Java extensions in IBM MDM | Catalogue all custom code; assess re-implementation in Reltio DQ rules |

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| MIG-INFO-001: Informatica MDM Hub to Reltio Migration | Reltio Asset Library |
| MIG-SAP-001: SAP MDG to Reltio Migration | Reltio Asset Library |
| MIG-OPC-001: On-Premise MDM to Cloud Migration | Reltio Asset Library |
| SVC-001: AI-Powered MDM Modernization | Reltio Asset Library |
| INT-001: Reltio REST API Integration Guide | Reltio Asset Library |