Reltio MDM Implementation Guide

Reltio Quick Start Program

Mastech Digital — Reltio MDM Platform Assets

90-day go-live for Customer MDM — proven methodology, pre-built assets

| Document | Reltio Quick Start Program |
| --- | --- |
| Category | ReltiLabs Service Offerings |
| Document ID | SVC-003 |
| Version | 1.0 |
| Date | March 2026 |
| Author | Mastech Digital — Reltio Practice |
| Reviewed By | Pending – Internal Review |
| Status | Draft |
| Classification | Internal – Mastech Digital |
| Platform Version | Reltio Cloud MDM – 2026 |
| Next Review | September 2026 |

# Executive Summary

The Reltio Quick Start Program is Mastech Digital's accelerated implementation offering for organizations starting their MDM journey or replacing legacy MDM systems. The program delivers a production-ready Customer MDM implementation in 90 days using pre-built configuration accelerators, proven methodology, and Mastech Digital's Reltio-certified delivery team.

# Table of Contents

1.0  Program Overview

2.0  90-Day Delivery Plan

3.0  Pre-Built Accelerators

4.0  Scope & Assumptions

5.0  Team Structure

6.0  Success Criteria

# 1. Program Overview

## 1.1 Program at a Glance

| Attribute | Details |
| --- | --- |
| Duration | 90 calendar days (approximately 13 weeks) |
| Scope | Customer MDM, 1-2 source systems |
| Platform | Reltio Cloud MDM (SaaS) |
| Delivery Model | Fixed-scope, time-boxed with defined milestones |
| Team | 1 Solution Architect + 1 MDM Engineer + 1 BA (part-time) |
| Investment | Starting from $125,000 (all-inclusive) |
| Outcome | Production Customer MDM with match/merge, governance, and integration |

## 1.2 What's Included

Reltio environment provisioning and baseline configuration

Customer entity type schema design and deployment

Match rule configuration (up to 10 rules, deterministic + fuzzy)

Survivorship strategy design and implementation

Source system integration for 1-2 systems (Salesforce, SAP, or custom)

Data quality rules implementation (up to 20 rules)

Stewardship workflow configuration

Basic monitoring and alerting setup

User training (up to 10 users)

Operations runbook and support handover

# 2. 90-Day Delivery Plan

## 2.1 Phase Breakdown

| Week | Phase | Key Activities | Milestone |
| --- | --- | --- | --- |
| 1-2 | Discovery & Design | Data profiling, source system analysis, schema design workshop, match rule design | Architecture Blueprint Approved |
| 3-4 | Foundation Setup | Reltio provisioning, schema deployment, user setup, connector configuration | Reltio Environment Ready |
| 5-8 | Core Build | Match rules, survivorship, DQ rules, source system ETL pipeline build | All Rules Configured |
| 9-10 | Integration Testing | End-to-end testing, match quality testing, DQ validation, performance testing | Test Sign-off |
| 11-12 | UAT & Training | Business user UAT, steward training, admin training, documentation | UAT Sign-off |
| 13 | Go-Live & Hypercare | Production deployment, go-live support, issue resolution | Live in Production |

## 2.2 Key Milestones

Day 10: Architecture Blueprint Approved — Reltio schema, match rules, and integration design finalized

Day 25: Reltio Environment Ready — All configuration deployed to Dev/Test environments

Day 55: Core Build Complete — All match rules, DQ rules, and ETL pipelines operational in Test

Day 70: Testing Complete — Integration test and performance test passed with sign-off

Day 83: UAT Sign-off — Business users accept Customer MDM functionality

Day 90: Production Go-Live — Customer MDM live with full monitoring and runbook

BEST PRACTICE

90-day delivery is achievable with pre-built accelerators. Success factors: executive sponsorship, 50% business stakeholder availability, clean source data, and dedicated IT support for integration.

# 3. Pre-Built Accelerators

## 3.1 Accelerator Library (included)

| Accelerator | Type | Saves |
| --- | --- | --- |
| Customer Entity Schema Template | Schema Config | 3-5 days of schema design |
| Salesforce Account/Contact Connector | Integration | 5-8 days of integration work |
| SAP Customer (KNA1) Connector | Integration | 5-8 days of integration work |
| Name Fuzzy Match Rule Pack (8 rules) | Match Rules | 4-6 days of rule development |
| Address Match Rule Pack (5 rules) | Match Rules | 3-4 days of rule development |
| Customer Survivorship Template | Survivorship | 2-3 days of design |
| DQ Rule Library (20 rules) | DQ Rules | 4-5 days of rule coding |
| Stewardship Workflow Template | Workflow | 2-3 days of workflow design |
| Monitoring Dashboard Template | Monitoring | 2-3 days of dashboard setup |
| Test Case Library (200 cases) | Testing | 5-7 days of test writing |

INFO

Mastech Digital's accelerator library reduces Quick Start implementation effort by 40-55%, enabling 90-day delivery vs 6-month standard MDM projects.

# 4. Scope & Assumptions

## 4.1 In Scope

Customer entity type (Individual and/or Organization)

Address, Phone, Email entity types (as supporting types)

Up to 2 source systems with batch ETL integration

Match and merge for Customer deduplication

Standard Reltio UI for stewardship

Basic API for downstream system consumption

## 4.2 Out of Scope

Product, Supplier, or other non-Customer MDM domains

More than 2 source system integrations

Real-time/event-driven integration (available in Accelerate tier)

Custom UI development

Data migration from legacy MDM (available as add-on)

## 4.3 Client Assumptions

Reltio Cloud MDM license procured before Day 1

Named Business Owner and Data Steward Lead available

Source system data extract capability (API or file)

IT environment team available for network/security configuration

Data samples available in Week 1 for profiling

# 5. Team Structure

| Role | Organization | Allocation | Responsibilities |
| --- | --- | --- | --- |
| Solution Architect | Mastech Digital | 100% | Technical leadership, architecture, match rule design, delivery ownership |
| MDM Engineer | Mastech Digital | 100% | Schema build, ETL development, DQ rules, testing |
| Business Analyst | Mastech Digital | 50% | Requirements, data mapping, stewardship design, training |
| Business Owner | Client | 25% | Scope decisions, UAT sign-off, change management |
| Data Steward Lead | Client | 50% | UAT, stewardship workflow validation, training participation |
| IT Lead | Client | 25% | Network/security, source system access, environment support |

# 6. Success Criteria

| Success Criterion | Measurement | Target |
| --- | --- | --- |
| Go-live on Day 90 | Production deployment date | Day 90 ± 5 days |
| Match Precision | Precision on gold set | >90% |
| Match Recall | Recall on gold set | >85% |
| DQ Score | Weighted DQ score on Customer data | >80% |
| System Performance | API response time (P95) | <500ms |
| User Acceptance | UAT sign-off | 100% of acceptance criteria passed |
| Training Completion | Users trained | 100% of target users trained |

BEST PRACTICE

Mastech Digital's Quick Start Program has a 100% on-time delivery record across 8 completed implementations as of Q1 2026.

# Related Assets

The following documents in the Mastech Digital Informatica Asset Library are related to this guide:

| Document | Category / Path |
| --- | --- |
| Reltio_AI_Powered_MDM_Modernization.docx | ReltiLabs/Service Offerings |
| RELTIO_MDM_Architecture_Guide.docx | Reltio Asset Library/01_Architecture |
| RELTIO_Operations_Runbook.docx | Reltio Asset Library/08_Operations |