CUTOVER CHECKLIST

Production Go-Live Execution Plan

Cutover Date: [DD-MMM-YYYY]   |   Wave: [Wave X]

# 1. Pre-Cutover Tasks (T-7 to T-1)

| # | Timeline | Task | Owner | Predecessor | Status | Sign-off |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | T-7 | Final code deployment to PROD | [Name] | - | PENDING | [ ] |
| 2 | T-5 | Stakeholder communication sent | [Name] | 1 | PENDING | [ ] |
| 3 | T-3 | Final parallel run reconciliation approved | [Name] | - | PENDING | [ ] |
| 4 | T-2 | Cutover runbook walkthrough complete | [Name] | - | PENDING | [ ] |
| 5 | T-1 | Go/No-Go decision meeting | [Name] | 3,4 | PENDING | [ ] |
| 6 | T-1 | War room setup confirmed | [Name] | - | PENDING | [ ] |

# 2. Cutover Day Tasks (T-0)

| # | Time | Task | Owner | Duration | Status | Sign-off |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 18:00 | Disable legacy scheduled jobs | [Name] | 15 min | PENDING | [ ] |
| 2 | 18:30 | Final data extraction from source systems | [Name] | 2 hrs | PENDING | [ ] |
| 3 | 20:30 | Execute final load to Fabric | [Name] | 3 hrs | PENDING | [ ] |
| 4 | 23:30 | Run reconciliation scripts | [Name] | 1 hr | PENDING | [ ] |
| 5 | 00:30 | Validate reconciliation results | [Name] | 30 min | PENDING | [ ] |
| 6 | 01:00 | Enable new pipelines/schedules | [Name] | 30 min | PENDING | [ ] |
| 7 | 01:30 | Smoke test downstream applications | [Name] | 1 hr | PENDING | [ ] |
| 8 | 02:30 | CUTOVER COMPLETE - Go/No-Go checkpoint | [Name] | - | PENDING | [ ] |

# 3. Post-Cutover Tasks (T+1 to T+7)

| # | Timeline | Task | Owner | Status | Sign-off |
| --- | --- | --- | --- | --- | --- |
| 1 | T+1 AM | Verify first production batch completed successfully | [Name] | PENDING | [ ] |
| 2 | T+1 | Monitor downstream reports/applications | [Name] | PENDING | [ ] |
| 3 | T+1 | Decommission legacy jobs (disable only) | [Name] | PENDING | [ ] |
| 4 | T+3 | Review and close cutover issues | [Name] | PENDING | [ ] |
| 5 | T+7 | Hypercare complete - transition to BAU support | [Name] | PENDING | [ ] |

# 4. Sign-off

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| [Cutover Lead] | Cutover Lead |  |  |
| [Business Owner] | Business Owner |  |  |