HYPERCARE &

STABILIZATION PLAN

Post-Go-Live Support Model for Data Modernization

Version 1.0 | Confidential

# Table of Contents

# 1. Executive Summary

The Hypercare period is the critical post-go-live phase where intensive support ensures successful adoption and stabilization of the modernized data platform. This plan defines the support model, escalation procedures, and exit criteria.

## 1.1 Hypercare Objectives

- Rapid Issue Resolution: Address production issues within SLA

- User Support: Help users adapt to new tools and processes

- Performance Monitoring: Ensure system meets performance targets

- Knowledge Transfer: Complete handover to operations team

- Stabilization: Achieve steady-state operations

# 2. Hypercare Timeline

## 2.1 Phase Definitions

┌─────────────────────────────────────────────────────────────────────┐

│                     HYPERCARE TIMELINE                              │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  GO-LIVE   WEEK 1-2      WEEK 3-4      WEEK 5-6      WEEK 7-8      │

│     │      CRITICAL      INTENSIVE     STANDARD      TRANSITION    │

│     ▼                                                               │

│  ───●──────────●──────────●──────────●──────────●──────────▶       │

│     │          │          │          │          │                  │

│     │  24/7    │  Extended │  Business │  Standard │  Steady       │

│     │  Support │  Hours    │  Hours    │  Support  │  State        │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

## 2.2 Support Coverage by Phase

| Phase | Duration | Coverage | Team Size |
| --- | --- | --- | --- |
| Critical | Week 1-2 | 24/7 | Full team + on-call rotation |
| Intensive | Week 3-4 | 6am-10pm | Full team, reduced on-call |
| Standard | Week 5-6 | Business hours | Core team + escalation |
| Transition | Week 7-8 | Business hours | Reduced team, handover |

# 3. Support Structure

## 3.1 Support Tiers

| Tier | Scope | Response | Resolution |
| --- | --- | --- | --- |
| L1 | How-to questions, access issues | 15 min | 1 hour |
| L2 | Application issues, data questions | 30 min | 4 hours |
| L3 | Complex technical, performance | 1 hour | 8 hours |
| L4 | Platform, architecture issues | 1 hour | 24 hours |

## 3.2 Escalation Matrix

| Severity | Definition | Initial Contact | Escalation |
| --- | --- | --- | --- |
| P1 - Critical | Production down | On-call lead | PM + Exec in 30m |
| P2 - High | Major function impaired | Team lead | PM in 2 hours |
| P3 - Medium | Workaround available | Support queue | Lead in 4 hours |
| P4 - Low | Minor issue | Support queue | Normal process |

# 4. Monitoring & Alerting

## 4.1 Key Metrics to Monitor

| Metric | Threshold | Alert | Owner |
| --- | --- | --- | --- |
| Pipeline success rate | > 99% | < 98% | Tech Lead |
| Job execution time | Within 20% of baseline | > 50% variance | Tech Lead |
| Data freshness | Per SLA | SLA breach | Data Owner |
| User logins | Baseline + growth | > 20% drop | Change Lead |
| Support ticket volume | Decreasing trend | > 20% increase | Support Lead |
| Error log volume | Baseline | > 3x baseline | Tech Lead |

# 5. Exit Criteria

## 5.1 Hypercare Exit Checklist

- No P1/P2 incidents open for 5+ business days

- Support ticket volume at or below baseline

- All critical jobs running successfully for 2+ weeks

- Operations team fully trained and confident

- Documentation complete and handed over

- Knowledge transfer sessions completed

- Runbooks tested and validated

- Client sign-off on stabilization

## 5.2 Handover Deliverables

| Deliverable | Description |
| --- | --- |
| Operations Runbook | Day-to-day procedures, troubleshooting guides |
| Architecture Documentation | System design, data flows, integrations |
| Monitoring Dashboards | Configured and documented dashboards |
| Incident Playbooks | Response procedures for known scenarios |
| Contact List | Escalation contacts with availability |
| Lessons Learned | Issues encountered and resolutions |

# Appendix: Document Information

| Document Title | Hypercare & Stabilization Plan |
| --- | --- |
| Version | 1.0 |
| Classification | Confidential |
| Last Updated | January 2025 |