DEPENDENCY

MANAGEMENT GUIDE

Tracking and Managing Migration Dependencies

Version 1.0 | Confidential

# Table of Contents

# 1. Overview

Dependencies are relationships between work items where one cannot start or complete until another is finished. Effective dependency management prevents delays and ensures smooth migration execution.

## 1.1 Dependency Types

| Type | Description & Examples |
| --- | --- |
| Technical | Code A must be converted before Code B (shared libraries, called programs) |
| Data | Table X must be loaded before Job Y can run (data pipelines) |
| Resource | Same SME needed for multiple assets, same environment for testing |
| External | Vendor deliverable, client decision, infrastructure provisioning |
| Logical | Business process order (monthly close before quarterly report) |

# 2. Dependency Identification

## 2.1 Discovery Methods

- Code Analysis: Static analysis of CALL statements, %INCLUDE, imports

- SME Interviews: Business knowledge of process dependencies

- Data Lineage: Trace data flow through systems

- Job Scheduling: Review existing schedule dependencies

- Documentation: Reference existing architecture docs

## 2.2 Dependency Matrix Example

| Asset | Depends On | Type | Status | Risk |
| --- | --- | --- | --- | --- |
| claims_summary.sas | util_macros.sas | Technical | Complete | Low |
| claims_summary.sas | member_dim table | Data | In Progress | Medium |
| monthly_report.sas | claims_summary.sas | Logical | Not Started | High |
| provider_load.dtsx | NPI file from vendor | External | Pending | High |

# 3. Managing Dependencies

## 3.1 Critical Path Analysis

CRITICAL PATH EXAMPLE

════════════════════════════════════════════════════════════════

Week 1      Week 2      Week 3      Week 4      Week 5

┌─────────┐

│util_mac │──┐

└─────────┘  │  ┌─────────┐

├─▶│claims   │──┐

┌─────────┐  │  │_summary │  │  ┌─────────┐    ┌─────────┐

│member   │──┘  └─────────┘  ├─▶│monthly  │───▶│quarterly│

│_dim     │                  │  │_report  │    │_close   │

└─────────┘  ┌─────────┐     │  └─────────┘    └─────────┘

│provider │─────┘

│_load    │  ◀── CRITICAL PATH (longest sequence)

└─────────┘

════════════════════════════════════════════════════════════════

## 3.2 Dependency Risk Mitigation

| Risk | Mitigation | Contingency |
| --- | --- | --- |
| Upstream delay | Early start, parallel work where possible | Stub/mock dependencies |
| External vendor late | Contractual SLAs, early escalation | Use sample data, defer asset |
| Resource conflict | Resource leveling, cross-training | Adjust sequence, add resources |
| Circular dependency | Refactor to break cycle | Convert together in single release |

# Appendix: Document Information

| Document Title | Dependency Management Guide |
| --- | --- |
| Version | 1.0 |
| Classification | Confidential |
| Last Updated | January 2025 |