ISSUE ESCALATION

PROCEDURES

Rapid Resolution of Migration Blockers

Version 1.0 | Confidential

# Table of Contents

# 1. Overview

Effective escalation ensures that issues are resolved at the appropriate level with the right urgency. This document defines when and how to escalate issues during the migration program.

## 1.1 Escalation Principles

- Early: Escalate before issues become crises

- Appropriate: Escalate to the right level, not too high or low

- Prepared: Come with analysis and recommended solutions

- Documented: All escalations are logged and tracked

- Closed Loop: Escalations are followed through to resolution

# 2. Escalation Levels

## 2.1 Escalation Matrix

| Level | Who | Issue Types | Response Time |
| --- | --- | --- | --- |
| L1 | Workstream Lead | Daily blockers, resource conflicts | Same day |
| L2 | Program Manager | Cross-team issues, scope questions | 24 hours |
| L3 | Program Leadership | Schedule/budget impact, vendor issues | 48 hours |
| L4 | Steering Committee | Major scope/timeline changes | 1 week |
| L5 | Executive Sponsor | Program viability, contract issues | As needed |

## 2.2 Escalation Triggers

| Trigger Condition | Escalate To | Timeline |
| --- | --- | --- |
| Blocker unresolved > 2 days | L2 - PM | Day 3 |
| Schedule slip > 1 week | L3 - Leadership | Immediate |
| Budget variance > $25K | L3 - Leadership | Immediate |
| Critical defect in production | L3 - Leadership | < 1 hour |
| Client escalation received | L3 - Leadership | < 4 hours |
| Scope change > 4 weeks | L4 - Steering | Next meeting |

# 3. Escalation Process

## 3.1 Escalation Workflow

ESCALATION WORKFLOW

════════════════════════════════════════════════════════════════

1. IDENTIFY & DOCUMENT

│  - Clearly define the issue

│  - Document impact (schedule, budget, quality)

│  - Identify what has been tried

▼

2. ASSESS ESCALATION LEVEL

│  - Use escalation matrix

│  - Dont skip levels unless emergency

▼

3. PREPARE ESCALATION PACKAGE

│  - Issue summary (1 paragraph)

│  - Impact assessment

│  - Options with pros/cons

│  - Recommended action

▼

4. ESCALATE

│  - Contact escalation point

│  - Provide escalation package

│  - Request specific decision or action

▼

5. TRACK & FOLLOW UP

- Log in issue tracker

- Follow up if no response in timeline

- Close when resolved

════════════════════════════════════════════════════════════════

# 4. Contact Information

## 4.1 Escalation Contacts

| Level | Primary | Backup | Contact Method |
| --- | --- | --- | --- |
| L1 | [Workstream Lead] | [Tech Lead] | Teams/Slack |
| L2 | [Program Manager] | [PM Backup] | Teams/Email |
| L3 | [Delivery Director] | [Account Lead] | Phone/Email |
| L4 | [VP Delivery] | [Client CTO] | Phone |
| L5 | [Partner] | [CEO] | Phone |

## 4.2 Emergency Escalation

For production incidents or security issues, skip normal levels and contact L3 immediately. Use the emergency hotline: [Phone Number]

# Appendix: Document Information

| Document Title | Issue Escalation Procedures |
| --- | --- |
| Version | 1.0 |
| Classification | Confidential |
| Last Updated | January 2025 |