MILESTONE SIGN-OFF

PROCEDURES

Formal Acceptance of Migration Deliverables

Version 1.0 | Confidential

# Table of Contents

# 1. Overview

Milestone sign-off is the formal process for obtaining stakeholder acceptance of completed deliverables. This ensures alignment between delivery team and client expectations.

## 1.1 Sign-off Principles

- Clear Criteria: Acceptance criteria defined before work begins

- Evidence-Based: Sign-off supported by documented proof

- Timely: Sign-off requested promptly upon completion

- Authoritative: Only designated approvers can sign off

- Binding: Sign-off constitutes formal acceptance

# 2. Milestone Definitions

## 2.1 Key Milestones

| Milestone | Deliverables | Approver |
| --- | --- | --- |
| M1: Discovery Complete | Inventory, complexity assessment, conversion plan | Client PM + Tech Lead |
| M2: Wave 1 SAS Complete | Converted code, test results, documentation | Client Tech Lead |
| M3: Wave 1 Informatica | Converted pipelines, test results | Client Tech Lead |
| M4: Wave 1 SSIS | Converted packages, test results | Client Tech Lead |
| M5: UAT Complete | UAT test results, defect resolution | Business Owner |
| M6: Go-Live | Production deployment, hypercare start | Executive Sponsor |
| M7: Project Close | Knowledge transfer, final documentation | Executive Sponsor |

# 3. Sign-off Process

## 3.1 Process Flow

MILESTONE SIGN-OFF WORKFLOW

════════════════════════════════════════════════════════════════

1. PREPARE SIGN-OFF PACKAGE (PM)

│  - Compile all deliverables

│  - Gather evidence of completion

│  - Complete self-assessment against criteria

▼

2. INTERNAL REVIEW (Tech Lead)

│  - Verify all criteria met

│  - Identify any gaps or concerns

│  - Recommend proceed or address gaps

▼

3. SUBMIT FOR SIGN-OFF

│  - Schedule review meeting

│  - Send package 3 days in advance

│  - Include sign-off form

▼

4. REVIEW MEETING

│  - Walk through deliverables

│  - Address questions

│  - Document any conditions

▼

5. OBTAIN SIGNATURE

│  - Approver signs form

│  - Note any conditions/exceptions

▼

6. ARCHIVE & COMMUNICATE

- Store signed form

- Announce milestone completion

════════════════════════════════════════════════════════════════

## 3.2 Sign-off Form Template

════════════════════════════════════════════════════════════════

MILESTONE SIGN-OFF FORM

════════════════════════════════════════════════════════════════

Project:      JHP Data Modernization

Milestone:    M2 - Wave 1 SAS Conversion Complete

Target Date:  January 31, 2025

Actual Date:  January 29, 2025

DELIVERABLES

────────────────────────────────────────────────────────────────

[ X ] 50 SAS programs converted to PySpark

[ X ] Unit tests passing (87% coverage)

[ X ] Data reconciliation complete (100% match)

[ X ] Performance benchmarks met

[ X ] Technical documentation updated

[ X ] Code deployed to SIT environment

ACCEPTANCE CRITERIA MET: [ X ] Yes  [ ] No  [ ] Partial

CONDITIONS/EXCEPTIONS:

None

APPROVAL

────────────────────────────────────────────────────────────────

Approver Name:  _____________________

Title:          _____________________

Signature:      _____________________

Date:           _____________________

════════════════════════════════════════════════════════════════

# Appendix: Document Information

| Document Title | Milestone Sign-off Procedures |
| --- | --- |
| Version | 1.0 |
| Classification | Confidential |
| Last Updated | January 2025 |