PROGRAM METRICS

& KPIs

Measuring Migration Success

Version 1.0 | Confidential

# Table of Contents

# 1. Overview

Program metrics provide objective measures of migration progress and health. This document defines the key performance indicators (KPIs) tracked throughout the program.

## 1.1 Measurement Principles

- Balanced: Track schedule, cost, quality, and scope

- Leading: Include predictive indicators, not just lagging

- Actionable: Metrics drive decisions and improvements

- Automated: Capture metrics through tools, minimize manual

- Visible: Dashboard accessible to all stakeholders

# 2. Key Performance Indicators

## 2.1 Schedule KPIs

| KPI | Target | Yellow | Red |
| --- | --- | --- | --- |
| Schedule Performance Index (SPI) | >= 0.95 | 0.90 - 0.94 | < 0.90 |
| Milestones On-Time | >= 90% | 75% - 89% | < 75% |
| Velocity (assets/week) | >= 50 | 35 - 49 | < 35 |
| Critical Path Slack (days) | >= 5 | 1 - 4 | <= 0 |

## 2.2 Cost KPIs

| KPI | Target | Yellow | Red |
| --- | --- | --- | --- |
| Cost Performance Index (CPI) | >= 0.95 | 0.90 - 0.94 | < 0.90 |
| Budget Variance | <= 5% | 5% - 10% | > 10% |
| Cost per Asset Converted | <= $2,500 | $2,500 - $3,500 | > $3,500 |
| Contingency Remaining | >= 50% | 25% - 49% | < 25% |

## 2.3 Quality KPIs

| KPI | Target | Yellow | Red |
| --- | --- | --- | --- |
| First-Pass Conversion Success | >= 85% | 75% - 84% | < 75% |
| Defect Density (per asset) | <= 0.5 | 0.5 - 1.0 | > 1.0 |
| Data Reconciliation Pass Rate | 100% | 99% | < 99% |
| Rework Rate | <= 10% | 10% - 20% | > 20% |

# 3. Metrics Dashboard

## 3.1 Executive Dashboard

════════════════════════════════════════════════════════════════

JHP DATA MODERNIZATION - PROGRAM DASHBOARD

As of January 10, 2025

════════════════════════════════════════════════════════════════

OVERALL HEALTH:  ● GREEN

SCHEDULE         COST             QUALITY          SCOPE

● GREEN          ● GREEN          ● GREEN          ● GREEN

SPI: 0.98        CPI: 1.02        FPR: 87%         CR: 3

CONVERSION PROGRESS

────────────────────────────────────────────────────────────────

SAS         ████████████░░░░░░░░  60%  (90/150)

Informatica ████████░░░░░░░░░░░░  40%  (400/1000)

SSIS        ██████░░░░░░░░░░░░░░  30%  (105/350)

────────────────────────────────────────────────────────────────

TOTAL       ████████░░░░░░░░░░░░  40%  (595/1500)

VELOCITY TREND (Assets/Week)

────────────────────────────────────────────────────────────────

Week 1: 45  Week 2: 48  Week 3: 52  Week 4: 55  Week 5: 58

Target: 50 ──▲

════════════════════════════════════════════════════════════════

# 4. Reporting Cadence

## 4.1 Metrics Review Schedule

| Report | Frequency | Audience | Owner |
| --- | --- | --- | --- |
| Daily Dashboard Update | Daily | Program team | Auto-generated |
| Weekly Metrics Report | Weekly | Leadership | PM |
| Monthly KPI Review | Monthly | Steering Committee | PM |
| Quarterly Business Review | Quarterly | Executives | Program Director |

# Appendix: Document Information

| Document Title | Program Metrics & KPIs |
| --- | --- |
| Version | 1.0 |
| Classification | Confidential |
| Last Updated | January 2025 |