QUALITY GATES &

CHECKPOINTS

Ensuring Quality at Every Stage of Migration

Version 1.0 | Confidential

# Table of Contents

# 1. Overview

Quality gates are formal checkpoints where work products must meet defined criteria before proceeding to the next phase. This document defines the gates, criteria, and approval process for the data modernization program.

## 1.1 Quality Gate Principles

- Mandatory: No work proceeds without passing the gate

- Measurable: Criteria are objective and verifiable

- Documented: All gate decisions are recorded

- Timely: Gate reviews occur at scheduled points, not ad-hoc

- Empowered: Gate reviewers have authority to stop work

# 2. Migration Quality Gates

## 2.1 Gate Overview

GATE 0          GATE 1          GATE 2          GATE 3          GATE 4

Discovery       Conversion      Testing         UAT             Go-Live

Complete        Complete        Complete        Complete        Approved

│               │               │               │               │

▼               ▼               ▼               ▼               ▼

┌──────┐       ┌──────┐       ┌──────┐       ┌──────┐       ┌──────┐

│Assess│──────▶│Convert│──────▶│ Test │──────▶│ UAT  │──────▶│Deploy│

└──────┘       └──────┘       └──────┘       └──────┘       └──────┘

## 2.2 Gate 0: Discovery Complete

| Criteria | Measure | Owner |
| --- | --- | --- |
| All source code inventoried | 100% catalogued | Tech Lead |
| Complexity assessment complete | All assets rated | Tech Lead |
| Dependencies mapped | Dependency matrix | Architect |
| SME interviews conducted | All critical assets | BA Lead |
| Conversion plan approved | Signed plan | PM |

## 2.3 Gate 1: Conversion Complete

| Criteria | Measure | Owner |
| --- | --- | --- |
| All code converted | 100% of scope | Workstream Lead |
| Unit tests written and passing | >= 80% coverage | Developer |
| Code review complete | All code reviewed | Tech Lead |
| Technical documentation updated | Docs current | Developer |
| Integration tests passing | 100% pass | QA Lead |

## 2.4 Gate 2: Testing Complete

| Criteria | Measure | Owner |
| --- | --- | --- |
| Data reconciliation passed | 100% match | QA Lead |
| Performance benchmarks met | <= Legacy time | Tech Lead |
| Regression suite passing | 100% pass | QA Lead |
| All defects resolved or deferred | 0 S1/S2 open | QA Lead |
| Test summary report approved | Signed report | PM |

## 2.5 Gate 3: UAT Complete

| Criteria | Measure | Owner |
| --- | --- | --- |
| All UAT test cases executed | 100% executed | UAT Lead |
| Business validation complete | SME sign-off | Client Lead |
| Critical defects resolved | 0 Critical open | QA Lead |
| Training delivered | All users trained | Change Lead |
| UAT sign-off obtained | Signed form | Client Lead |

# 3. Gate Review Process

## 3.1 Review Meeting

- Schedule: Gate reviews scheduled 2 weeks in advance

- Attendees: Gate owner, PM, Tech Lead, Client Lead, QA Lead

- Duration: 1-2 hours depending on gate complexity

- Materials: Evidence package distributed 3 days prior

- Decision: Pass, Conditional Pass (with actions), or Fail

# Appendix: Document Information

| Document Title | Quality Gates & Checkpoints |
| --- | --- |
| Version | 1.0 |
| Classification | Confidential |
| Last Updated | January 2025 |