RISK MANAGEMENT

PLAYBOOK

Proactive Identification and Mitigation of Migration Risks

Version 1.0 | Confidential

# Table of Contents

# 1. Overview

This playbook defines the approach for identifying, assessing, mitigating, and monitoring risks throughout the data modernization program. Proactive risk management prevents issues from becoming crises.

## 1.1 Risk Management Principles

- Proactive: Identify risks before they become issues

- Transparent: All risks visible to appropriate stakeholders

- Owned: Every risk has a single accountable owner

- Actionable: Mitigation plans are specific and executable

- Monitored: Regular review of risk status and effectiveness

# 2. Risk Categories

## 2.1 Migration-Specific Risk Categories

| Category | Description & Examples |
| --- | --- |
| Technical | LLM conversion accuracy, performance degradation, integration failures, data quality issues |
| Resource | Staff availability, skill gaps, key person dependencies, vendor capacity |
| Schedule | Dependency delays, scope creep, underestimated complexity, parallel project conflicts |
| Business | Requirements changes, stakeholder availability, organizational changes, competing priorities |
| Compliance | HIPAA violations, audit findings, data governance gaps, security vulnerabilities |
| Operational | Production stability, rollback complexity, support readiness, knowledge transfer |

# 3. Risk Assessment

## 3.1 Probability and Impact Scales

| Level | Probability | Schedule Impact | Cost Impact |
| --- | --- | --- | --- |
| 5 - Critical | > 80% | > 4 weeks delay | > $500K |
| 4 - High | 60-80% | 2-4 weeks delay | $200K - $500K |
| 3 - Medium | 40-60% | 1-2 weeks delay | $50K - $200K |
| 2 - Low | 20-40% | < 1 week delay | $10K - $50K |
| 1 - Minimal | < 20% | < 2 days delay | < $10K |

## 3.2 Risk Score Matrix

IMPACT

1     2     3     4     5

┌─────┬─────┬─────┬─────┬─────┐

5 │  5  │ 10  │ 15  │ 20  │ 25  │  CRITICAL (20-25)

├─────┼─────┼─────┼─────┼─────┤

4 │  4  │  8  │ 12  │ 16  │ 20  │  HIGH (12-19)

PROB.    ├─────┼─────┼─────┼─────┼─────┤

3 │  3  │  6  │  9  │ 12  │ 15  │  MEDIUM (6-11)

├─────┼─────┼─────┼─────┼─────┤

2 │  2  │  4  │  6  │  8  │ 10  │  LOW (1-5)

├─────┼─────┼─────┼─────┼─────┤

1 │  1  │  2  │  3  │  4  │  5  │

└─────┴─────┴─────┴─────┴─────┘

# 4. Top Migration Risks

## 4.1 Pre-Identified Risk Register

| Risk | P | I | Mitigation Strategy |
| --- | --- | --- | --- |
| LLM conversion accuracy below target | 3 | 4 | Iterative testing, human review, fallback to manual |
| Legacy code undocumented/complex | 4 | 3 | SME interviews, code analysis tools, extra buffer |
| Key SME availability limited | 3 | 4 | Early engagement, dedicated allocation, backup SMEs |
| Scope creep from discovered complexity | 4 | 3 | Strict change control, contingency budget |
| Production data issues discovered late | 3 | 4 | Early data profiling, parallel runs, reconciliation |
| Performance regression in converted code | 2 | 4 | Performance benchmarks, optimization sprints |
| Resistance to change from legacy teams | 3 | 3 | Change management, training, involvement |

# 5. Risk Response Strategies

## 5.1 Response Types

| Strategy | Description & When to Use |
| --- | --- |
| Avoid | Eliminate the risk by changing approach. Use when risk is unacceptable and alternatives exist. |
| Mitigate | Reduce probability or impact through proactive actions. Most common response. |
| Transfer | Shift risk to another party (insurance, contracts). Use for specialized risks. |
| Accept | Acknowledge and monitor without active mitigation. Use for low-impact risks. |

## 5.2 Risk Review Cadence

- Daily: Workstream leads review active risks in standups

- Weekly: Program status includes risk register review

- Bi-weekly: Dedicated risk review meeting with mitigation owners

- Monthly: Steering committee reviews critical and high risks

# Appendix: Document Information

| Document Title | Risk Management Playbook |
| --- | --- |
| Version | 1.0 |
| Classification | Confidential |
| Last Updated | January 2025 |