SCOPE CHANGE

CONTROL PROCESS

Managing Scope While Maintaining Delivery Momentum

Version 1.0 | Confidential

# Table of Contents

# 1. Overview

Scope change control ensures that modifications to project scope are evaluated, approved, and implemented in a controlled manner. This process balances the need for flexibility with the discipline required for successful delivery.

## 1.1 Change Control Principles

- No Unauthorized Changes: All scope changes go through formal process

- Impact Assessment: Every change is evaluated for schedule, cost, and risk

- Appropriate Authority: Changes approved at the right level

- Traceability: Complete audit trail of all change requests

- Communication: All stakeholders informed of approved changes

# 2. Change Categories

## 2.1 Change Classification

| Category | Definition | Approval | Timeline |
| --- | --- | --- | --- |
| Minor | < 1 week effort, no budget impact | Program Manager | 2 days |
| Moderate | 1-4 weeks effort, < $50K impact | Program Leadership | 1 week |
| Major | > 4 weeks effort or > $50K impact | Steering Committee | 2 weeks |
| Critical | Fundamental scope/timeline change | Executive Sponsor | As needed |

# 3. Change Request Process

## 3.1 Process Flow

CHANGE REQUEST WORKFLOW

════════════════════════════════════════════════════════════════

1. SUBMIT REQUEST

│  Requestor completes Change Request Form

│  Includes: Description, justification, urgency

▼

2. INITIAL TRIAGE (1 day)

│  Program Manager reviews for completeness

│  Assigns category and impact assessment owner

▼

3. IMPACT ASSESSMENT (2-5 days)

│  Technical: Effort, complexity, dependencies

│  Schedule: Timeline impact, critical path

│  Cost: Budget impact, resource needs

│  Risk: New risks introduced

▼

4. REVIEW & DECISION

│  Appropriate authority reviews assessment

│  Decision: Approve / Reject / Defer / Need Info

▼

5. IMPLEMENT (if approved)

│  Update project plan, communicate to team

│  Track as part of normal delivery

▼

6. CLOSE

Document outcome, update lessons learned

════════════════════════════════════════════════════════════════

## 3.2 Change Request Form

| Field | Description |
| --- | --- |
| CR Number | Auto-generated unique identifier (CR-2025-001) |
| Requestor | Name, role, contact information |
| Date Submitted | Date of initial submission |
| Title | Brief descriptive title |
| Description | Detailed description of the requested change |
| Business Justification | Why is this change needed? What is the business value? |
| Urgency | Critical / High / Medium / Low |
| Affected Assets | Which converted programs/pipelines are affected? |
| Proposed Solution | If known, how should this be implemented? |

# 4. Impact Assessment Template

## 4.1 Assessment Checklist

- Effort Estimate: Hours/days by role required to implement

- Schedule Impact: Effect on current timeline and milestones

- Cost Impact: Additional budget required (if any)

- Resource Impact: New skills or additional staff needed

- Dependency Impact: Effect on other workstreams or projects

- Risk Impact: New risks introduced by the change

- Testing Impact: Additional testing required

- Documentation Impact: Updates to specifications, runbooks, etc.

## 4.2 Decision Criteria

| Factor | Consideration |
| --- | --- |
| Business Value | Does the benefit justify the cost and risk? |
| Timing | Can this wait until a future phase or release? |
| Alternatives | Are there lower-impact ways to achieve the same goal? |
| Precedent | Will approving this open the door to similar requests? |
| Commitment | Do we have the resources to deliver this alongside existing scope? |

# 5. Change Control Metrics

- Change Request Volume: Number of CRs submitted per week

- Approval Rate: Percentage of CRs approved vs rejected

- Processing Time: Average days from submission to decision

- Implementation Success: Percentage of approved CRs delivered on time

- Scope Creep Index: Total approved effort vs original baseline

# Appendix: Document Information

| Document Title | Scope Change Control Process |
| --- | --- |
| Version | 1.0 |
| Classification | Confidential |
| Last Updated | January 2025 |